## European Affairs Section
Annex 8
List of MA on-the-spot inspections
Period monitored: from 1. 1. to 31. 12. 2009
Number | Name of beneficiary | Project title ITMS code | Date: |  | Date of completion of on-the-spot check report | Oprávnené náklady projektu (aktuálne kontrahovanie) |  |  | Amount of funding checked |  |  | Funding checked as percentage of the eligible costs of the project |  |  | Main findings and proposals, including any irregularities identified | Information on the performance / non-performance of corrective measures within the set deadline
|  |  | start of check | end of check |  | ESF | ŠR | Vlastné | ESF | SB | Own funds | ESF | SB | Own funds
1. | National Institute for Education | 26110130001 | 2009-06-08 | 2009-06-27 | 2009-07-01 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | The control group identified the following deficiencies: - out of date personnel matrices; missing CVs and consent statements for the processing of personal data, - deficiencies in publicity for the project, in particular provision for publicity during education activities, - delay in the contract award procedure for the purchase of data projectors, notebooks and screens for the schools of the project participants and subsequently in their delivery to participants’ schools, - dates and times of education activities not updated on website - low quality in the preparation of monitoring reports, - a low level of control activity by project coordinators in relation to the organisation of education activities, failure to ensure effective and efficient grouping of participants in education groups (the number the language skills of participants), - failure to ensure standardisation of materials and textbooks necessary for education. The control group requests that the missing CVs and consent statements for personal data processing be added to the personnel matrices and delivered to the MA by the specified in table 1 of the on-the-spot check report (15.08.2009). The control group also requests: Completion of the contract award process for the purchase and delivery of data projectors, notebooks, textbooks and screens to schools and project participants by 30.09.2009. Delivery of standard teaching materials to project participants by 30.09.2009. In order to correct the deficiencies in publicity, the control group requests that the beneficiary issue guidelines on project publicity to project coordinators and tutors by 30.09.2009 so that publicity is provided in accordance the Manual for Beneficiaries, the General Contractual Conditions and the Manual for Information and Publicity starting from the education activities taking place in the next period. The control group requests that other deficiencies be eliminated on an ongoing basis. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
2. | National Institute for Education | 26140130001 | 2009-06-08 | 2009-06-27 | 2009-07-01 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | The control group identified the following deficiencies: - out of date personnel matrices; missing CVs and consent statements for the processing of personal data, - deficiencies in publicity for the project, in particular provision for publicity during education activities, - delay in the contract award procedure for the purchase of data projectors, notebooks and screens for the schools of the project participants and subsequently in their delivery to participants’ schools, - dates and times of education activities not updated on website - low quality in the preparation of monitoring reports, - failure to ensure standardisation of materials and textbooks necessary for education. The control group requests that the missing CVs and consent statements for personal data processing be added to the personnel matrices and delivered to the MA by the specified in table 1 of the on-the-spot check report (15.08.2009). The control group also requests: Completion of the contract award process for the purchase and delivery of data projectors, notebooks, textbooks and screens to schools and project participants by 30.09.2009. Delivery of standard teaching materials to project participants by 30.09.2009. In order to correct the deficiencies in publicity, the control group requests that the beneficiary issue guidelines on project publicity to project coordinators and tutors by 30.09.2009 so that publicity is provided in accordance the Manual for Beneficiaries, the General Contractual Conditions and the Manual for Information and Publicity starting from the education activities taking place in the next period. The control group requests that other deficiencies be eliminated on an ongoing basis. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
3. | National Institute for Education | 26120130001 | 2009-06-08 | 2009-06-27 | 2009-06-29 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | The control group identified the following deficiencies: - missing CVs and consent statements for the processing of personal data, - deficiencies in publicity for the project, in particular provision for publicity during education activities The control group requests that the missing CVs and consent statements for personal data processing be added to the personnel matrices and delivered to the MA by the specified in table 1 of the on-the-spot check report. In order to correct the deficiencies in publicity, the control group requests that the beneficiary issue guidelines on project publicity to project coordinators and tutors by 30.09.2009 so that publicity is provided in accordance the Manual for Beneficiaries, the General Contractual Conditions and the Manual for Information and Publicity starting from the education activities taking place in the school year 2009/2010. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
4. | National Institute for Education | 26140230001 | 2009-06-08 | 2009-06-27 | 2009-06-29 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | The control group identified the following deficiencies: - missing CVs and consent statements for the processing of personal data, - deficiencies in publicity for the project, in particular provision for publicity during education activities The control group requests that the missing CVs and consent statements for personal data processing be added to the personnel matrices and delivered to the MA by the specified in table 1 of the on-the-spot check report. Although the control group cannot report deficiencies in publicity for the project in education activities for the objective Regional Competitiveness and Employment, it recommends the same corrective measures for deficiencies in publicity as for the Convergence objective in view of the deficiencies in publicity identified with regard to this objective. In order to correct the deficiencies in publicity, the control group requests that the beneficiary issue guidelines on project publicity to project coordinators and tutors by 30.09.2009 so that publicity is provided in accordance the Manual for Beneficiaries, the General Contractual Conditions and the Manual for Information and Publicity starting from the education activities taking place in the school year 2009/2010. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
5. | Institute of Information and Prognoses of Education | 26110130083 | 2009-06-22 | 2009-06-22 | 2009-07-08 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | Discrepancy with measurable indicators Since it is not possible to change the value for a measurable indicator, the beneficiary will not achieve the contracted value, which will have a financial impact. The beneficiary must change the settings of the criteria used to select teachers from individual schools. We recommend adding additional categories to the criteria for 250 pupils and above (250–300 pupils at secondary school – 3 teachers, 300–500 pupils at secondary school – 5 teachers etc.) depending on the current structure of schools. The beneficiary should request a change in annex no. 6 of the Grant agreement “Detailed description of the project – target group” giving justification for the change and the new formula for setting the number of teachers to take part in education. The beneficiary was warned that it is necessary to identify the project or use the project title in publicity according to the relevant objective. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
6. | Institute of Information and Prognoses of Education | 26140130013 | 2009-06-22 | 2009-06-22 | 2009-07-08 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | The beneficiary was urged to eliminate the following identified deficiencies: Discrepancy with measurable indicators Since it is not possible to change the value for a measurable indicator, the beneficiary will not achieve the contracted value, which will have a financial impact. The beneficiary must change the settings of the criteria used to select teachers from individual schools. We recommend adding additional categories to the criteria for 250 pupils and above (250-300 pupils at secondary school – 3 teachers, 300–500 pupils at secondary school – 5 teachers etc.) depending on the current structure of schools. The beneficiary should request a change in annex no. 6 of the Grant agreement “Detailed description of the project - target group” giving justification for the change and the new formula for setting the number of teachers to take part in education. The beneficiary was warned that it is necessary to identify the project or use the project title in publicity according to the relevant objective. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
7. | Institute of Information and Prognoses of Education | 26110130084 | 2009-06-22 | 2009-06-22 | 2009-07-08 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | The beneficiary was urged to eliminate the following identified deficiencies: Discrepancy with measurable indicators Since it is not possible to change the value for a measurable indicator, the beneficiary will not achieve the contracted value, which will have a financial impact. The beneficiary must change the settings of the criteria used to select teachers from individual schools. We recommend adding additional categories to the criteria for 250 pupils and above (250-300 pupils at secondary school – 3 teachers, 300–500 pupils at secondary school – 5 teachers etc.) depending on the current structure of schools. The beneficiary should request a change in annex no. 6 of the Grant agreement “Detailed description of the project - target group” giving justification for the change and the new formula for setting the number of teachers to take part in education. The beneficiary was warned that it is necessary to identify the project or use the project title in publicity according to the relevant objective. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
8. | Institute of Information and Prognoses of Education | 26140130014 | 2009-06-22 | 2009-06-22 | 2009-07-08 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | The beneficiary was urged to eliminate the following identified deficiencies: Discrepancy with measurable indicators Since it is not possible to change the value for a measurable indicator, the beneficiary will not achieve the contracted value, which will have a financial impact. The beneficiary must change the settings of the criteria used to select teachers from individual schools. We recommend adding additional categories to the criteria for 250 pupils and above (250-300 pupils at secondary school – 3 teachers, 300–500 pupils at secondary school – 5 teachers etc.) depending on the current structure of schools. The beneficiary should request a change in annex no. 6 of the Grant agreement “Detailed description of the project - target group” giving justification for the change and the new formula for setting the number of teachers to take part in education. The beneficiary was warned that it is necessary to identify the project or use the project title in publicity according to the relevant objective. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
9. | State Institute for Vocational Education | 26110130085 | 2009-10-07 | 2009-10-08 | 2009-11-02 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | 1. Storage of documents • The control group recommends keeping the Grant agreement together with its addenda in the archive of the project manager and providing copies of the agreement and its addenda to administrative staff. The control group also recommends that documentation be kept separately for Convergence and for RC&E. • Add to the documentation all missing documents not presented to the control group. 2. Correspondence between documents archived by the Ministry of Education and by the beneficiary • Submit all personnel matrices archived by the beneficiary to the sponsor • Add all missing monitoring reports submitted to the provider to the documentation • Separate monitoring documentation relating to Convergence and to RC&E 3. Conformity between project implementation and the Grant agreement • Request a change in the agreement, Annex No. 5 Detailed description of activities, regarding the start of activity 2.2. • Regularly submit all approved methodological materials and all outputs from each activity as an annex to the monitoring report. • Request a change in the agreement, Annex no. 5 Detailed description of activities regarding activity 3.1 – publication of a multimedia DVD. • In the supplement Education, publish technical articles suitable for the supplement presenting the latest knowledge in the fields of education, science, R&D. 4. Compliance with publicity rules • Correct errors in logos on methodological material • Put up an information poster on the beneficiary’s building General recommendations • The control group has several times recommended keeping separate documentation for Convergence and for RC&E This applies to all documentation including contracts, addenda, personnel matrices, monitoring reports, methodological instructions and various outputs of activities. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
10. | State Institute for Vocational Education | 26140130015 | 2009-10-07 | 2009-10-08 | 2009-11-02 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | 1. Storage of documents • The control group recommends keeping the Grant agreement together with its addenda in the archive of the project manager and providing copies of the agreement and its addenda to administrative staff. The control group also recommends that documentation be kept separately for Convergence and for RC&E. • Add to the documentation all missing documents not presented to the control group. 2. Correspondence between documents archived by the Ministry of Education and by the beneficiary • Submit all personnel matrices archived by the beneficiary to the sponsor • Add all missing monitoring reports submitted to the provider to the documentation • Separate monitoring documentation relating to Convergence and to RC&E 3. Conformity between project implementation and the Grant agreement • Request a change in the agreement, Annex No. 5 Detailed description of activities, with regard to the start of activity 2.2 • Regularly submit all approved methodological materials and all outputs from each activity as an annex to the monitoring report. • Request a change in the agreement, Annex no. 5 Detailed description of activities regarding activity 3.1 – publication of a multimedia DVD. 4. Compliance with publicity rules • Correct errors in logos on methodological material • Put up an information poster on the beneficiary’s building. General recommendations • The control group has several times recommended keeping separate documentation for Convergence and for RC&E This applies to all documentation including contracts, addenda, personnel matrices, monitoring reports, methodological instructions and various outputs of activities. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
11. | Methodological and Pedagogical Centre | 26110130087 | 2009-11-25 | 2009-11-25 | 2010-01-22 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | 1. verification that the substantial implementation of the project is in line with the agreement on provision of a non-reimbursable financial contribution (the Grant Agreement) and the objective of the project expressed in terms of measurable indicators, the budget, the project implementation schedule etc. - the control group recommends the submission to the Sponsor of all relevant outputs for activity 1.1 (in accordance with the above recommendations of the On-the-spot Check Report) for the assessment of the start of activity implementation) and if they are not submitted the beneficiary should ask the MA to amend the Grant Agreement Annex 5 Detailed description of project activities with regard to the start of activity 1.1 (if the relevant outputs are not submitted for assessment of the start of activity implementation) by means of an addendum, - submit copies of attendance lists for the pilot education activities for activity 1.2 - ask the MA to amend the Grant Agreement Annex 5 Detailed description of project activities with regard to the start of activity 2.2 by means of an addendum and - ask the MA to amend the Grant Agreement Annex 5 Detailed description of project activities with regard to the start of activity 2.3 (see the notes on activity 2.3) by means of an addendum. 2. check whether the beneficiary submits correct information on physical progress in the implementation of the project in monitoring reports. - give more detailed information in the monitoring report on the implementation of specific activities that reflects physical progress in the implementation of the project. 3. check that personnel matrices are up to date. - correct formal deficiencies in the personnel matrices - submit missing contracts/agreements from the personnel matrices to the Beneficiary's project file. 4. check whether the documents submitted to the MA correspond to documents held by the beneficiary. Does not apply 5. check of compliance with publicity rules. - place an information poster on the beneficiary’s building, - conform to all publicity requirements for document presentation laid down by the Grant agreement (in invitations, attendance sheets, minutes, programmes, articles and the like). | The measures adopted to address deficiencies are being implemented on an ongoing basis.
12. | Methodological and Pedagogical Centre | 26140130017 | 2009-11-25 | 2009-11-25 | 2010-01-22 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | 1. verification that the substantial implementation of the project is in line with the agreement on provision of a non-reimbursable financial contribution (the Grant Agreement) and the objective of the project expressed in terms of measurable indicators, the budget, the project implementation schedule etc. - the control group recommends the submission to the Provider of all relevant outputs for activity 1.1 (in accordance with the above recommendations of the On-the-spot Check Report) for the assessment of the start of activity implementation) and if they are not submitted the beneficiary should ask the MA to amend the Grant Agreement Annex 5 Detailed description of project activities with regard to the start of activity 1.1 (if the relevant outputs are not submitted for assessment of the start of activity implementation) by means of an addendum, - ask the MA to amend the Grant Agreement Annex 5 Detailed description of project activities with regard to the start of activity 2.2 by means of an addendum and - ask the MA to amend the Grant Agreement Annex 5 Detailed description of project activities with regard to the start of activity 2.3 (see the notes on activity 2.3) by means of an addendum. 2. check whether the beneficiary submits correct information on physical progress in the implementation of the project in monitoring reports. - give more detailed information in the monitoring report on the implementation of specific activities that reflects physical progress in the implementation of the project. 3. check that personnel matrices are up to date. - eliminate formal deficiencies in the personnel matrices - submit missing contracts/agreements from the personnel matrices to the Beneficiary's project file. 4. check whether the documents submitted to the MA correspond to documents held by the beneficiary. - divide monitoring documentation between the Convergence and RC&E fields, - add to the Beneficiary’s documentation the missing external communication with the Provider, add the Grant agreement, which was not checked by the control group on the spot to the Beneficiaries project file. 5. verification of compliance with publicity rules. - place an information poster on the beneficiary’s building, - conform to all publicity requirements for document presentation laid down by the Grant agreement (in invitations, attendance sheets, minutes, programmes, articles and the like). | The measures adopted to address deficiencies are being implemented on an ongoing basis.
13. | State school inspectorate | 26110130088 | 2009-10-12 | 2009-10-12 | 2009-10-19 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | 1. Training activity 1.1 took place 12–13.10.2009 in accordance with the “Project Implementation Schedule”. The two-day meeting of the management of the School Inspection Centres took place before the start of training for school inspectors that, according to the Beneficiary, should take place in the periods 20–22.10.2009 and 28–30.10.2009 in the Hotel Šachtička in Banská Bystrica. The purpose of the meeting was to familiarise the directors and heads of department of the school inspection centres with the organisation and content of the project. Technical aspects of particular project activities were presented to managers. Other activities at the meeting included the selection of 7 elementary and 7 secondary schools to sign an Grant agreement under ASFEU calls no. OPV/2008/1.1/03-SORO and OPV/2008/1.1/04-SORO and the agreement of deadlines for the performance of tasks and the preparation of output. The managers received a “Methodology for comprehensive inspections in elementary schools” and a “Methodology for comprehensive inspections in secondary schools”. The event was well-organised and the content was in accordance with Annex No. 5 of the Grant Agreement “Detailed description of project activities”. 2. The management of the school inspection centres falls within the target group for the project but is not part of the measurable result indicator “Number of employees participating in project training activities”. This will be achieved after the completion of training activity 1.1, in which 84 school inspectors will participate according to the Grant Agreement. 3. Conformity with the monitored horizontal priority “Sustainable development” cannot be checked because so far only preparatory measures have been taken for training activities. It will be possible to check conformity after the completion of training activity 1.1 and fulfilment of the measurable indicator “Number of employees participating in project training activities”, to which the horizontal priority applies. 4. The training location was identified by a clearly visible poster advertising the implementation of the project. The information poster did not, however, include the declaration specified in the Grant Agreement, General contractual conditions, article 4(2)(c). Because the project is a mirror, the Beneficiary was reminded of the need to distinguish between the objectives (measures) that the project implements. The provided documents such as the training material, questionnaire and invitation were correctly labelled. As part of the publicity for the project the Beneficiary provided promotional items – a stand and flags of Slovakia and the EU, which were given to participants. 5. The control group found that the personnel matrix for the project was not up to date and did not include the tutors for activity 1.1. This information was communicated to the Beneficiary, which undertook to supply an up-to-date personnel matrix as soon as possible. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
14. | State school inspectorate | 26140130018 | 2009-10-16 | 2009-10-16 | 2009-10-19 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | 1. Training activity 1.1 took place on 16.10.2009 in accordance with the “Project Implementation Schedule”. The meeting of the management of the School Inspection Centres took place before the start of training for school inspectors that, according to the Beneficiary, should take place in the period 26–27.10.2009 in the Beneficiary’s headquarters. The purpose of the meeting was to familiarise the management of the school inspection centre with the organisation and content of the project. Technical aspects of particular project activities were presented to managers. Other activities at the meeting included the selection of 2 elementary and 2 secondary schools to sign an Grant agreement under ASFEU calls no. OPV/2008/4.1/03-SORO and OPV/2008/4.1/04-SORO and the agreement of deadlines for the performance of tasks and the preparation of output. The managers received a “Methodology for comprehensive inspections in elementary schools” and a “Methodology for comprehensive inspections in secondary schools”. The event was well-organised and the content was in accordance with Annex No. 5 of the Grant Agreement “Detailed description of project activities”. 2. The management of the school inspection centre falls within the target group for the project but is not part of the measurable result indicator “Number of employees participating in project training activities”. This will be fulfilled after the completion of training activity 1.1, in which 12 school inspectors are expected to participate. 3. Conformity with the monitored horizontal priority “Sustainable development” cannot be checked because so far only preparatory measures have been taken for training activities. It will be possible to check conformity after the completion of training activity 1.1 and fulfilment of the measurable indicator “Number of employees participating in project training activities”, to which the horizontal priority applies. 4. The training location was identified by a clearly visible poster advertising the implementation of the project. The information poster did not, however, include the declaration specified in the Grant Agreement, General contractual conditions, article 4(2)(c). Because the project is a mirror, the Beneficiary was reminded of the need to distinguish between the objectives (measures) that the project implements. The provided documents such as the training material, questionnaire and invitation were correctly labelled. As part of the publicity for the project the Beneficiary provided promotional items – a stand and flags of Slovakia and the EU, which were given to participants. 5. The control group found that the personnel matrix for the project was not up to date and did not include the tutors for activity 1.1. This information was communicated to the Beneficiary, which undertook to supply an up-to-date personnel matrix as soon as possible. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
15. | Ministry of Education | 26150130007 | 2009-12-09 | 2009-12-09 | 2010-01-07 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | no findings | n/a
16. | Ministry of Education | 26140330007 | 2009-12-09 | 2009-12-09 | 2010-01-07 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | no findings | n/a
17. | Ministry of Education | 26150130008 | 2009-12-09 | 2009-12-09 | 2010-01-07 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | no significant findings | n/a
18. | Ministry of Education | 26140330008 | 2009-12-09 | 2009-12-09 | 2010-01-07 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | no significant findings | n/a
19. | State Institute for Vocational Education | 26110130086 | 2009-12-14 | 2009-12-15 | 2010-01-20 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | 1. Check for conformity between project implementation and the Grant Agreement – review the activity of the project manager reject financial claims of the Beneficiary relating to meetings between technical supervisors and the authors of the study “New technologies in education” on the grounds that attendance lists have not been provided as evidence of the meetings; deliver the final assessment report and review on the technical study “New technologies in education” (by 28.02.2010) the Beneficiary should propose other means for monitoring the quality of preparation of the study “New technologies in education” besides assessment reports and reviews and incorporate the proposal into a request for a change in Annex No. 5 of the Grant Agreement request amendment of Annex No. 5 of the Grant Agreement in the section on obtaining feedback so that it is clear how the comments of teaching staff using the technical study “New technologies in education” in the teaching process will be taken into account in the revision and correction of the text with regard to the change in the monitoring of the quality of preparation of the study. distribute the Analysis of the needs and requirements of the labour market in the automobile industry (Needs Analysis) and the Occupational analysis for the automobile industry (DACUM Analysis) to teaching staff and schools participating in the project (by 31.01.2010) deliver the half-yearly evaluation report on the technical study “Quality management in the automobile industry” (by 28.02.2010) the Beneficiary should propose other means for monitoring the quality of preparation of the study “Quality management in the automobile industry” besides evaluation reports and reviews and incorporate the proposal into a request for a change in Annex 5 of the Grant Agreement request amendment of Annex No. 5 of the Grant Agreement in the section on obtaining feedback so that it is clear how the comments of teaching staff using the technical study “Quality management in the automobile industry” in the teaching process will be taken into account in the revision and correction of the text with regard to the change in the monitoring of the quality of preparation of the study. request a change in Annex No. 2 of the Grant Agreement – “Purpose of support” as regards the conditions for the indicator in order to reconcile Annex No. 2 and Annex No. 5 of the Grant Agreement. request a change in Annex No. 5 of the Grant Agreement as regards the change in the development of a school curriculum for a two-year study programme with the extension of the deadline to 15.02.2010 and the development of a school curriculum for a two-year study subject with a deadline to 30.06.2010 deliver the school curriculum for the two-year study programme to the MA (by 28.02.2010) deliver the plan for the number of textbooks for the first year of the four-year study subject together with the real date for the completion of the textbooks (by 15.02.2010) request a change in Annex No. 5 of the Grant Agreement due to the change in the number of textbooks for both study subjects based on experience submit a written justification for the alternative method of teaching without textbooks, school curricula and the developed multimedia classrooms in the request for a change to the Agreement. submit original copies of the opinions and recommendations of the seven self-governing regions as to which schools should participate in the project “Development of new curricula in vocational education to meet the needs of the automobile industry II” (by 31.01.2010) submit post facto confirmation of the five-years teaching experience of all teaching staff participating in the project and satisfying the requirement for five years’ experience (by 15.02.2010). Only such teaching staff will be recognised as eligible beneficiaries. rejection of the financial claims of the Beneficiary associated with the selection of the target group of employees in the following schools: Specialised secondary school for technology, F. Lipku 2422/5, Hlohovec; Specialised secondary school for trade and services, Námestie sv. Martina 5, Holíč; Combined school – specialised secondary school for the automobile industry, Školská 7, Banská Bystrica; Specialised secondary school, Zvolenská cesta č. 83, Lučenec; Specialised polytechnic secondary school, Jelšavská 404, Dolný Kubín – Kňažia; Combined school, Hattalova 471, Nižná; Combined school, Červenej armády 25, Martin; Transport academy, Rosinská cesta 2, Žilina; Specialised secondary school for transport, Zelená 2, Martin – Priekopa; Specialised secondary school, Ostrovského 1, Košice; Specialised secondary school for technology, Partizánska 1, Michalovce; Specialised secondary school, Markušovská cesta 4, Spišská Nová Ves; Juraj Henisch Combined school, Slovenská 5, Bardejov; Specialised secondary school, SNP 16, Sabinov; Specialised secondary school for technology, Okružná 693, Čadca; Specialised secondary school for transport, Konštantínova 2, Prešov; specialised secondary school for the automobile industry, Coburgova 7859/39 Trnava on the grounds of failure to comply with the deadline for the selection of the target group of teaching staff or on the grounds of failure to provide proof of compliance with the set deadline resubmission of separate proof of eligibility of the target group of teaching staff with current dates for objective C and objective RC&E including all particulars (school stamp, date, position of the eligible person) without a claim for additional funds (by 31.03.2010). classification of one of the teachers in the Specialised secondary school for the automobile industry, Moldavská cesta 2, Košice as a member of the ineligible target group as a result of the training of 6 teachers from this institution in contravention of Annex No. 5 of the Grant Agreement, which sets a limit of five teachers per school the Beneficiary shall conclude a cooperation agreement with each school, a cooperation agreement with the Higher-tier Territorial Authority in each region; schools shall conclude agreements with firms (for the provision of specialised training and vocational experience) and pilot centres no later than the installation of the computer classrooms; a change to Annex No. 5 of the Grant Agreement shall be requested for this purpose resubmit to the MA confirmation of the target group of pupils from the Specialised secondary school for transport in Martin, the Specialised secondary school for trade and services in Galanta, the Specialised secondary school for transport in Prešov, the Combined school – Specialised secondary school in Banská Bystrica, the specialised secondary school for the automobile industry in Košice and the Juraj Ribay specialised secondary school in Bánovce nad Bebravou with the current date (by 31.03.2010) without entitlement to additional funding. deliver the Rules for project management and the Publicity manual to the MA (by 31.01.2010) request a change in Annex No. 5 of the Grant Agreement regarding an extension of the period for development of multimedia textbooks deliver to every school participating in the project a curriculum in printed form and to the teaching staff participating in the project a curriculum in electronic format together with the other materials specified in activity 1.2 of the project (by 31.01.2010) request a change in Annex No. 5 of the Grant Agreement regarding the failure to meet the deadline for the start of provision of education via e-learning request a change in Annex No. 5 of the Grant Agreement regarding the possibility for other schools and other members of teaching staff and pupils in secondary schools delivery of copies of class books from schools participating in the project to the MA (by 31.01.2010) and their subsequent reporting as annexes in the relevant monitoring reports at the end of each half year and school year (next in monitoring report no. 4 to 15.04.2010) delivery of copies of class books for vocational experience and specialist training from schools participating in the project (by 31.01.2010) and their subsequent reporting as annexes in the relevant monitoring reports at the end of each half year and school year (next in monitoring report no. 4 to 15.04.2010) rejection of the financial claims of the Beneficiary for the meeting between the technical supervisors and the authors of the studies “Soft skills” and “Communication technology in manufacturing” 2. Check whether the beneficiary’s monitoring reports provide correct information on physical progress in the implementation of the project and the performance of other duties under the Grant Agreement The control group recommends rejecting financial claims relating to the submitted annexes to monitoring report no. 1 of 19.08.2009 (Attendance sheet for the Project Steering Committee (RVP) and working meetings) and recommends payment for only the first meeting of the RVP if the beneficiary submits a report from the meeting (by 31.01.2009). In spite of this the control group recommends the submission of a brief report on the other meetings (by 31.01.2010) The control group recommends rejecting financial claims relating to the submitted annexes to monitoring report no. 2 of 03.12.2009 (Attendance sheet for the RVP and working meetings) only in the case of the meeting of 25.08.2009; in spite of this it recommends that a brief report of this meeting be submitted by 31.01.2010. It requests submission of minutes of other meetings by 31.01.2010. The control group warns the beneficiary that if corrective action is not taken and the beneficiary does not deliver the minutes of the meetings by the deadline for the monitoring reports, the beneficiary will not be reimbursed even if these materials are delivered subsequently 4. check of compliance with publicity rules correct the length of project implementation, add the type of project to the poster for information and publicity, make a better quality poster display a poster or other medium to provide information and publicity in the room to be used in training activity 2.3 and that will subsequently be used for project meetings label files to show clearly that there are two different projects (objective C and objective RC&E). Separate the cover sheets for the two projects deliver the materials Analysis of the requirements and needs of the labour market in the automobile industry, Occupational analysis for the automobile industry and the Curriculum in a form satisfying the conditions for information and publicity to both teaching staff and schools, in accordance with Annex No. 5 of the Grant Agreement by 31.01.2010. update the website for the project 5. check whether documents submitted to the MA correspond to the documents kept by the beneficiary The control group recommends that the beneficiary comply with the formal requirements for requests submitted to the MA including archiving of documents by the beneficiary. The control group recommends that the beneficiary pay increased attention in the submission of requests to the secretariat of the MA and stamp requests from 17.06.2009 with the stamp of the State Institute for Vocational Education to ensure uniformity between the documents archived by the beneficiary and the provider. (by 31.01.2010) The control group requests submission of the original of addendum no. 1 (by 31.01.2010). To ensure greater transparency, the control group recommends keeping all correspondence relating to the project (originals of letters, copies of change requests and electronic correspondence) in a single file (sent and received post). The originals of change requests and their annexes should be archived in the file of addenda and copies of letters relating to monitoring reports and personnel matrices should be kept in their respective files (the file for monitoring reports and the file for personnel matrices). The control group recommends that the beneficiary pay increased attention to the archiving of annexes of the monitoring reports submitted to the MA in order to ensure that the documents are identical and also add the missing appendices to each monitoring report (by 31.01.2010) The control group recommends visibly marking the personnel table for the project for objective C and the project for objective RC&E and to add the mail addresses of all persons included in the personnel table – from the next personnel table The control group recommends adding the missing CVs and the missing consent statements of affected persons in all personnel matrices (by 28.02.2010) | The measures adopted to address deficiencies are being implemented on an ongoing basis.
20. | State Institute for Vocational Education | 26140130016 | 2009-12-14 | 2009-12-15 | 2010-01-20 |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | 1. Check for conformity between project implementation and the Grant Agreement – review the activity of the project manager reject financial claims of the Beneficiary relating to meetings between technical supervisors and the authors of the study “New technologies in education” on the grounds that attendance lists have not been provided as evidence of the meetings; deliver the final assessment report and review assessment on the technical study “New technologies in education” (by 28.02.2010) the Beneficiary should propose other means for monitoring the quality of preparation of the study “New technologies in education” besides and assessment reports and reviews and incorporate the proposal into a request for a change in Annex 5 of the Grant Agreement request amendment of Annex No. 5 of the Grant Agreement in the section on obtaining feedback so that it is clear how the comments of teaching staff using the technical study “New technologies in education” in the teaching process will be taken into account in the revision and correction of the text with regard to the change in the monitoring of the quality of preparation of the study. distribute the Analysis of the needs and requirements of the labour market in the automobile industry (Needs Analysis) and the Occupational analysis for the automobile industry (DACUM Analysis) to teaching staff and schools participating in the project (by 31.01.2010) deliver the half-yearly evaluation report on the technical study “Quality management in the automobile industry” (by 28.02.2010) the Beneficiary should propose other means for monitoring the quality of preparation of the study “Quality management in the automobile industry” besides evaluation reports and reviews and incorporate the proposal into a request for a change in Annex 5 of the Grant Agreement request amendment of Annex No. 5 of the Grant Agreement in the section on obtaining feedback so that it is clear how the comments of teaching staff using the technical study “Quality management in the automobile industry” in the teaching process will be taken into account in the revision and correction of the text with regard to the change in the monitoring of the quality of preparation of the study. request a change in Annex No. 2 of the Grant Agreement – “Purpose of support” as regards the conditions for the indicator in order to reconcile Annex No. 2 and Annex No. 5 of the Grant Agreement. to request a change in Annex No. 5 of the Grant Agreement as regards the change in the development of a school curriculum for a two-year study programme with the extension of the deadline to 15.02.2010 and the development of a school curriculum for a two-year study subject with a deadline to 30.06.2010 deliver the school curriculum for the two-year study programme to the MA (by 28.02.2010) deliver the plan for the number of textbooks for the first year of the four-year study subject together with the real date for the completion of the textbooks (by 15.02.2010) request a change in Annex No. 5 of the Grant Agreement due to the change in the number of textbooks for both study subjects based on experience submit a written justification for the alternative method of teaching without textbooks, school curricula and the developed multimedia classrooms in the request for a change to the Agreement. submit original copies of the opinions and recommendations of Bratislava self–governing region as to which schools should participate in the project “Development of new curricula in vocational education to meet the needs of the automobile industry II” (by 31.01.2010) The control group requests a written explanation of the method for the selection of the fourth school participating in four-year subject – the Specialised secondary school of technology, Vranovská 4, Bratislava – which is not found in the opinion of Bratislava Self-governing Region (by 31.01.2010) submit post facto confirmation of the five-years teaching experience of all teaching staff participating in the project and satisfying the requirement for five years’ experience (by 15.02.2010). Only such teaching staff will be recognised as eligible beneficiaries. rejection of the financial claims of the Beneficiary associated with the selection of the target group of employees in the following schools: Specialised secondary school of technology, Vranovská 4, Bratislava, Specialised secondary school, Kysucká 14, Senec, Specialised secondary school for transport, Sklenárova 9, Bratislava on the grounds of failure to comply with the deadline for the selection of the target group of teaching staff or on the grounds of failure to provide proof of compliance with the set deadline resubmission of separate proof of eligibility of the target group of teaching staff with current dates for objective C and objective RC&E including all particulars (school stamp, date, position of the eligible person) without a claim for additional funds (by 31.03.2010). the Beneficiary shall conclude a cooperation agreement with each school, a cooperation agreement with the Higher-tier Territorial Authority; schools shall conclude agreements with firms (for the provision of specialised training and vocational experience) and the pilot centre no later than the installation of the computer classrooms; a change to Annex No. 5 of the Grant Agreement shall be requested for this purpose resubmit to the MA confirmation of the target group of pupils from the Specialised secondary school for transport (by 31.03.2010) without entitlement to additional funding deliver the Rules for project management and the Publicity manual to the MA (by 31.01.2010) request a change in Annex No. 5 of the Grant Agreement regarding an extension of the period for development of multimedia textbooks deliver to every school participating in the project a curriculum in printed form and to the teaching staff participating in the project a curriculum in electronic format together with the other materials specified in activity 1.2 of the project (by 31.01.2010) request a change in Annex No. 5 of the Grant Agreement regarding the failure to meet the deadline for the start of provision of education via e-learning request a change in Annex No. 5 of the Grant Agreement regarding the possibility for other members of teaching staff and pupils in secondary schools with a written explanation of the situation. delivery of copies of class books from schools participating in the project to the MA (by 31.01.2010) and their subsequent reporting as annexes in the relevant monitoring reports at the end of each half year and school year (next in monitoring report no. 4 to 15.04.2010) delivery of copies of class books for vocational experience and specialist training from schools participating in the project (by 31.01.2010) and their subsequent reporting as annexes in the relevant monitoring reports at the end of each half year and school year (next in monitoring report no. 4 to 15.04.2010) rejection of the financial claims of the Beneficiary for the meeting between the technical supervisors and the authors of the studies “Soft skills” and “Communication technology in manufacturing” 2. Check whether the beneficiary’s monitoring reports provide correct information on physical progress in the implementation of the project and the performance of other duties under the Grant Agreement The control group recommends rejecting financial claims relating to the submitted annexes Attendance sheet for the Project Steering Committee (RVP) and working meetings on monitoring report no. 1 of 19.08.2009 and recommends payment for only the first meeting of the RVP if the beneficiary submits a report from the meeting (by 31.01.2009). In spite of this the control group recommends the submission of a brief report on the other meetings (by 31.01.2010) The control group recommends rejecting financial claims relating to the submitted annexes to monitoring report no. 2 of 03.12.2009 (Attendance sheet for the Project Steering Committee (RVP) and working meetings) only in the case of the meeting of 25.08.2009. In spite of this the control group recommends the submission of a brief report on this meeting by 31.01.2010. In the case of the other meetings the control group requests submission of the minutes by 31.01.2010. The control group has warned the beneficiary that if the situation is not corrected and the beneficiary does not deliver the minutes of meetings by the deadline for monitoring reports, the beneficiary will not be paid for these meetings even if the materials are delivered later 4. check of compliance with publicity rules correct the length of project implementation, add the type of project to the poster for information and publicity, make a better quality poster display a poster or other medium to provide information and publicity in the room to be used in training activity 2.3 and that will subsequently be used for project meetings label files to show clearly that there are two different projects (objective C and objective RC&E). Separate the cover sheets for the two projects deliver the materials Analysis of the requirements and needs of the labour market in the automobile industry, Occupational analysis for the automobile industry and the Curriculum in a form satisfying the conditions for information and publicity to both teaching staff and schools, in accordance with Annex No. 5 of the Grant Agreement by 31.01.2010. update the website for the project 5. check whether documents submitted to the MA correspond to the documents kept by the beneficiary The control group recommends that the beneficiary comply with the formal requirements for requests submitted to the MA including archiving of documents by the beneficiary. The control group recommends that the beneficiary pay increased attention in the submission of requests to the secretariat of the MA and stamp requests from 17.06.2009 with the stamp of the State Institute for Vocational Education to ensure uniformity between the documents archived by the beneficiary and the provider. (by 31.01.2010) To ensure greater transparency, the control group recommends keeping all correspondence relating to the project (originals of letters, copies of change requests and electronic correspondence) in a single file (sent and received post). The originals of change requests and their annexes should be archived in the file of addenda and copies of letters relating to monitoring reports and personnel matrices should be kept in their respective files (the file for monitoring reports and the file for personnel matrices). The control group recommends that the beneficiary pay increased attention to the archiving of annexes of the monitoring reports submitted to the MA in order to ensure that the documents are identical and also add the missing appendices to each monitoring report (by 31.01.2010) The control group recommends visibly marking the personnel table for the project for objective C and the project for objective RC&E and to add the mail addresses of all persons included in the personnel table - from the next personnel table The control group recommends adding the missing CVs and the missing consent statements of affected persons in all personnel matrices (by 28.02.2010) | The measures adopted to address deficiencies are being implemented on an ongoing basis.

## Finance Section for EU SF
Number | Name of beneficiary | Project title ITMS code | Date: |  | Date of completion of on-the-spot check report | Eligible costs of project (currently contracted) |  |  | Amount of funding checked |  |  | Funding checked as percentage of the eligible costs of the project |  |  | Main findings of the on-the-spot check | Main conclusions and recommendations, including any irregularities identified | Information on the performance / non-performance ocorrective measures within the set deadline
|  |  | start of check | end of check |  | ESF | SB | Own funds | ESF | SB | Own funds | ESF | SB | Own funds
1. | National Institute for Education | 26110130001 | 2009-06-08 | 2009-08-05 | 2009-08-18 |  |  | n/a | 43959.81 |  | n/a | 61.23% |  | n/a | Breach of Act No. 553/2003 Z.z., breach of the Labour Code Act No. 523/2004 Z.z., deficiencies in cumulative time sheets, inadequate specification of activities reported in individual time sheets, overlapping personnel costs. | 1. The beneficiary – employer shall ensure that the deficiencies identified in the findings are corrected in the next payment request based on time sheets – by specifying or describing in detail the project activities and the results of the scheduled project activities for each time sheet for the month reported on; 2. The beneficiary – employer shall review, in accordance with the findings, the employment contracts and job descriptions of employees working on the project as employees (of the same employer) and implement the urgent corrective measures in this area. 3. The beneficiary – employer shall ensure that the identified deficiencies are corrected and that employees are correctly registered and work correct reported in employment on projects in the National Institute for Education (NIE). 4. The beneficiary – employer shall ensure that the identified deficiencies are eliminated by adding to existing management regulations of the NIE or producing new ones so that rules on records of attendance and the place of work conform with the labour code. 5. The beneficiary – employer shall appoint (through an agreement on work activities / employment contract) an internal employee – competent person or an external competent person to carry out public procurement activities for projects and shall not use contractually provided legal services (at a rate of SKK 1 700 per hour) for these activities (including consultation) as in this case such services are unjustified and uneconomic. 6. The beneficiary – employer shall review the compensation of internal employees (managers and service personnel) for work on projects and make changes to compensation in accordance with the employment contract and the section of the current Manual for Grant applicants on national projects so that compensation is in line with the limits for expenditure and personnel costs in the organisation; 7. The beneficiary – employer shall review the official positions of employees contracted to work on projects. The aim should be to simplify the reporting of work and pay either by extending the job description in the employment contract for the employee’s main employment according to their position in the project or by revising and maintaining the employment contract for main employment and a subordinate employment contract for work on the project. The review should consider changes that reflect the conditions for project implementation, bearing in mind the need to carry out the employer’s tasks and to comply with the Labour Code. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
2. | National Institute for Education | 26140130001 | 2009-06-08 | 2009-08-05 | 2009-08-18 |  |  | n/a | 4020.96 |  | n/a | 61.41% |  |  | Breach of Act No. 553/2003 Z.z., breach of the Labour Code Act No. 523/2004 Z.z., deficiencies in cumulative time sheets, inadequate specification of activities reported in individual time sheets, overlapping personnel costs. | 1. The beneficiary – employer shall ensure that the deficiencies identified in the findings are corrected in the next payment request based on time sheets – by specifying or describing in detail the project activities and the results of the scheduled project activities for each time sheet for the month reported on; 2. The beneficiary - employer shall review, in accordance with the findings, the employment contracts and job descriptions of employees working on the project as employees (of the same employer) and implement the urgent corrective measures in this area. 3. The beneficiary – employer shall ensure that the identified deficiencies are corrected and that employees are correctly registered and work correct reported in employment on projects in the National Institute for Education (NIE). 4. The beneficiary – employer shall ensure that the identified deficiencies are eliminated by adding to existing management regulations of the NIE or producing new ones so that rules on records of attendance and the place of work conform with the labour code. 5. The beneficiary - employer shall appoint (through an agreement on work activities / employment contract) an internal employee – competent person or an external competent person to carry out public procurement activities for projects and shall not use contractually provided legal services (at a rate of SKK 1 700 per hour) for these activities (including consultation) as in this case such services are unjustified and uneconomic. 6. The beneficiary – employer shall review the compensation of internal employees (managers and service personnel) for work on projects and make changes to compensation in accordance with the employment contract and the section of the current Manual for Grant applicants on national projects so that compensation is in line with the limits for expenditure and personnel costs in the organisation; 7. The beneficiary - employer shall review the official positions of employees contracted to work on projects. The aim should be to simplify the reporting of work and pay either by extending the job description in the employment contract for the employee’s main employment according to their position in the project or by revising and maintaining the employment contract for main employment and a subordinate employment contract for work on the project. The review should consider changes that reflect the conditions for project implementation, bearing in mind the need to carry out the employer’s tasks and to comply with the Labour Code. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
3. | National Institute for Education | 26120130001 | 2009-06-08 | 2009-08-05 | 2009-09-21 |  |  | n/a | 25232.99 |  | n/a | 76.81% |  |  | Breach of Act No. 553/2003 Z.z., breach of the Labour Code Act No. 523/2004 Z.z., deficiencies in cumulative time sheets, inadequate specification of activities reported in individual time sheets, overlapping personnel costs. | 1. Comply consistently in practice with the relevant provisions of Act No. 553/2003 Z.z. on the remuneration of certain employees performing work in the public interest and the amendment of certain acts and Act No. 311/2001 Z.z. the Labour Code 2. Sign official employment record certificates (zápočtové listy) to ensure that employees working on the project are assigned to the correct pay class and pay grade in accordance with Act No. 553/2003 Z.z. on the remuneration of certain employees performing work in the public interest and the amendment of certain acts (its annexes). 3. Specify in detail the activities referred to in the work statements in order to avoid or limit the identification of ineligible expenditures by the MA. 4. Ensure consistent recording of working time for every employee participating in the project by means of electronic records of attendance or an attendance book or basic support documentation used to document the real number of hours worked on both projects claimed in the time sheets. 5. When preparing pay summaries for the relevant month, consistently respect the particulars of employment contracts (working time) or work performance agreements (weekly working time) while taking into consideration also data on individual periods of work (time performing work for the project). 6. In accordance with Act No. 431/2002 Z.z. on accounting , as amended, keep and record monthly balances or extracts from accounts for each project (805 and 806), in particular the general ledger and journal. 7. When making a claim for a proportion of eligible expenditure on goods and services divided between the two projects, consistently apply the percentage ratio for the proportion of financing allocated to each project within the overall budget of the national project (i.e. 87:13). 8. In order to ensure economy, efficiency and purposefulness in the use of public funds (Act No. 524/2003 Z.z. on budgetary rules in public administration and the amendment of certain acts) review the possibility of performing certain activities (e.g. activities whose character is identical or similar to activities carried out within the main employment of internal employees) based on an employment contract or an addendum to the job description (extension of the job description) | The measures adopted to address deficiencies are being implemented on an ongoing basis.
4. | National Institute for Education | 26140230001 | 2009-06-08 | 2009-08-05 | 2009-09-21 |  |  | n/a | 4976.74 |  | n/a | 70.61% |  |  | Breach of Act No. 553/2003 Z.z., breach of the Labour Code Act No. 523/2004 Z.z., deficiencies in cumulative time sheets, inadequate specification of activities reported in individual time sheets, overlapping personnel costs. | 1. Comply consistently in practice with the relevant provisions of Act No. 553/2003 Z.z. on the remuneration of certain employees performing work in the public interest and the amendment of certain acts and Act No. 311/2001 Z.z. the Labour Code 2. Sign official employment record certificates (zápočtové listy) to ensure that employees working on the project are assigned to the correct pay class and pay grade in accordance with Act No. 553/2003 Z.z. on the remuneration of certain employees performing work in the public interest and the amendment of certain acts (its annexes). 3. Specify in detail the activities referred to in the work statements in order to avoid or limit the identification of ineligible expenditures by the MA. 4. Ensure consistent recording of working time for every employee participating in the project by means of electronic records of attendance or an attendance book or basic support documentation used to document the real number of hours worked on both projects claimed in the time sheets. 5. When preparing pay summaries for the relevant month, consistently respect the particulars of employment contracts (working time) or work performance agreements (weekly working time) while taking into consideration also data on individual periods of work (time performing work for the project). 6. In accordance with Act No. 431/2002 Z.z. on accounting , as amended, keep and record monthly balances or extracts from accounts for each project (805 and 806), in particular the general ledger and journal. 7. When making a claim for a proportion of eligible expenditure on goods and services divided between the two projects, consistently apply the percentage ratio for the proportion of financing allocated to each project within the overall budget of the national project (i.e. 87:13). 8. In order to ensure economy, efficiency and purposefulness in the use of public funds (Act No. 524/2003 Z.z. on budgetary rules in public administration and the amendment of certain acts) review the possibility of performing certain activities (e.g. activities whose character is identical or similar to activities carried out within the main employment of internal employees) based on an employment contract or an addendum to the job description (extension of the job description) | The measures adopted to address deficiencies are being implemented on an ongoing basis.
5. | Institute of Information and Prognoses of Education | 26110130083 | 2009-09-30 | 2009-11-04 | 2009-12-11 |  |  | n/a | 29979.04 |  | n/a | 60.05% |  |  | Check of cumulative time sheets (recommended by control group – classification of activities according to the set key) and their comparison with records of attendance (electronic and written) identified some discrepancies in data on entry into and departure from employment, in the recording or taking into account of lunch breaks in accordance with the relevant internal regulation on the recording of working time, in claims for convalescent leave for periods not relating to project implementation. | 1. Ensure conformity with keying for individual activities based on the objectives and the target groups (set by the beneficiary) and subsequent claiming of the appropriate amount (financial sum) of personnel costs taking into consideration the breakdown of eligible pay (i.e. respect for the gross pay and insurance contributions for the given calendar month – total labour costs, and factors affecting the amount of eligible costs). 2. Ensure consistent recording of working time for every employee participating in projects by means of electronic records of attendance or an attendance book or basic support documentation used to document the real number of hours worked on projects and the incorporation of data from these records into time sheets (while respecting basic working time, breaks for lunch, holidays etc.). 3. When claiming the proportion of eligible expenditure on goods and services allocated to each project or mirror, consistently apply the proportion – key based on the number of schools or the number of teachers participating in each project (target groups and objectives) set by the beneficiary in accordance with the measurable indicators set out in the detailed description of the project. 4. Consistently comply with the conditions set in the project budget – e.g. unit prices | The measures adopted to address deficiencies are being implemented on an ongoing basis.
6. | Institute of Information and Prognoses of Education | 26140130013 | 2009-09-30 | 2009-11-04 | 2009-12-11 |  |  | n/a | 3871.24 |  | n/a | 54.33% |  |  | Check of cumulative time sheets (recommended by control group - classification of activities according to the set key) and their comparison with records of attendance (electronic and written) identified some discrepancies in data on entry into and departure from employment, in the recording or taking into account of lunch breaks in accordance with the relevant internal regulation on the recording of working time, in claims for convalescent leave for periods not relating to project implementation. | 1. Ensure conformity with keying for individual activities based on the objectives and the target groups (set by the beneficiary) and subsequent claiming of the appropriate amount (financial sum) of personnel costs taking into consideration the breakdown of eligible pay (i.e. respect for the gross pay and insurance contributions for the given calendar month – total labour costs, and factors affecting the amount of eligible costs). 2. Ensure consistent recording of working time for every employee participating in projects by means of electronic records of attendance or an attendance book or basic support documentation used to document the real number of hours worked on projects and the incorporation of data from these records into time sheets (while respecting basic working time, breaks for lunch, holidays etc.). 3. When claiming the proportion of eligible expenditure on goods and services allocated to each project or mirror, consistently apply the proportion – key based on the number of schools or the number of teachers participating in each project (target groups and objectives) set by the beneficiary in accordance with the measurable indicators set out in the detailed description of the project. 4. Consistently comply with the conditions set in the project budget – e.g. unit prices | The measures adopted to address deficiencies are being implemented on an ongoing basis.
7. | Institute of Information and Prognoses of Education | 26110130084 | 2009-09-30 | 2009-11-04 | 2010-01-04 |  |  | n/a | 21349.46 |  | n/a | 69.97% |  |  | Check of cumulative time sheets (recommended by control group - classification of activities according to the set key) and their comparison with records of attendance (electronic and written) identified some discrepancies in data on entry into and departure from employment, in the recording or taking into account of lunch breaks in accordance with the relevant internal regulation on the recording of working time, in claims for convalescent leave for periods not relating to project implementation. | 1. Ensure conformity with keying for individual activities based on the objectives and the target groups (set by the beneficiary) and subsequent claiming of the appropriate amount (financial sum) of personnel costs in relation to the classification of eligible pay. 2. Ensure consistent recording of working time for every employee participating in projects by means of electronic records of attendance or an attendance book or basic support documentation used to document the real number of hours worked on projects and the incorporation of data from these records into time sheets while respecting basic working time, breaks for lunch, holidays etc. 3. When claiming the proportion of eligible expenditure on goods and services allocated to each project or mirror, consistently apply the proportion – key based on the number of schools or the number of teachers participating and the objectives set by the beneficiary in accordance with the measurable indicators set out in the detailed description of project 26110130084, 26140130014. 4. Consistently comply with the conditions set in the project budget – e.g. unit prices 5. Claims for fuel costs relating to the service use of a motor vehicle in project implementation must include at least one member of the project team for projects with ITMS code 26110130084 and 26140130014. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
8. | Institute of Information and Prognoses of Education | 26140130014 | 2009-09-30 | 2009-11-04 | 2010-01-04 |  |  | n/a | 5 690,37 € |  | n/a | 71.34% |  |  | Check of cumulative time sheets (recommended by control group - classification of activities according to the set key) and their comparison with records of attendance (electronic and written) identified some discrepancies in data on entry into and departure from employment, in the recording or taking into account of lunch breaks in accordance with the relevant internal regulation on the recording of working time, in claims for convalescent leave for periods not relating to project implementation. | 1. Ensure conformity with keying for individual activities based on the objectives and the target groups (set by the beneficiary) and subsequent claiming of the appropriate amount (financial sum) of personnel costs in relation to the classification of eligible pay. 2. Ensure consistent recording of working time for every employee participating in projects by means of electronic records of attendance or an attendance book or basic support documentation used to document the real number of hours worked on projects and the incorporation of data from these records into time sheets while respecting basic working time, breaks for lunch, holidays etc. 3. When claiming the proportion of eligible expenditure on goods and services allocated to each project or mirror, consistently apply the proportion - key based on the number of schools or the number of teachers participating and the objectives set by the beneficiary in accordance with the measurable indicators set out in the detailed description of project 26110130084, 26140130014. 4. Consistently comply with the conditions set in the project budget – e.g. unit prices 5. Claims for fuel costs relating to the service use of a motor vehicle in project implementation must include at least one member of the project team for projects with ITMS code 26110130084 and 26140130014. | The measures adopted to address deficiencies are being implemented on an ongoing basis.
9. | Methodological and Pedagogical Centre | 26110130087 | 2009-12-03 | 2010-02-25 | 2010-02-25 |  |  | n/a | 32 707,-€ |  | n/a | 18.17% |  |  | Findings of the control group when checking statements no. 1 and 2/2009 - discrepancy between the cost and the commentary on the budget in item 1.2.2 – the function is not eligible to draw from the stated item. The beneficiary breached point 1(i) of article 14 Eligible Costs of Annex No. 1 of the Grant Agreement – General Contractual Conditions The advert in HN did not include the required particulars for publicity: The article does not refer to the added value of EU activity – Modern education for a knowledge society / The project is co-financed from EU funds in accordance with article 4(2)(c) of Annex No. 1 of the Grant Agreement – General Contractual Terms and Conditions. In the programme on TA3 the broadcast of an incomplete and non-identical text of the Declaration was identified. The beneficiary breached point 2(c) of article 4 – Publicity and Information – of Annex No. 1 of the Grant Agreement – General Contractual Terms and Conditions |  | The measures adopted to address deficiencies are being implemented on an ongoing basis.
10. | Methodological and Pedagogical Centre | 26140130017 | 2009-12-03 | 2010-02-25 | 2010-02-25 |  |  | n/a | 2021.6 |  | n/a | 38% |  |  | The beneficiary did not submit a bank statement proving the transfer of pay and postage costs from the project account (7000182192/8180) to the expenditure account of the MPC (7000063679/8180). The Beneficiary breached the condition laid down in article 15(1)(1.6) of Annex No. 1 of the Grant Agreement. | The beneficiary may claim the costs claimed in Payment Request No. 5 (settlement of advance payment) in a subsequent payment request because the actual implementation of payments satisfies the conditions for refunding (interim payment). | The measures adopted to address deficiencies are being implemented on an ongoing basis.