## Hárok3
Annex No. 10: Comparison of planned and actual drawing of national projects as of 31 Dec. 2011* (in EUR)
Year | 2007 |  |  | 2008 |  |  | 2009 |  |  | 2010 |  |  | 2011 |  |  | 2012 |  |  | 2013 |  |  | 2014 |  |  | TOTAL
Project name | Planned budget (SF+SB) | Actual drawing (ST+SB) | Progress in drawing in % | Planned budget (SF+SB) | Actual drawing (SF+SB)** | Progress in drawing in % | Planned budget (SF+SB) | Actual drawing (SF+ŠR) | Progress in drawing in % | Planned budget (SF+SB) | Actual drawing (SF+SB) | Progress in drawing in % | Planned budget (SF+SB) | Actual drawing (SF+SB) | Progress in drawing in % | Planned budget (SF+SB) | Actual drawing (SF+SB) | Progress in drawing in % | Planned budget (SF+SB) | Actual drawing (SF+SB) | Progress in drawing in % | Planned budget (SF+SB) | Actual drawing (SF+SB) | Progress in drawing in % | Total amount of conracted funds NP (SF+SB) | Total cumulative drawing of funds (SF+SB) | Total cumulative drawing in %
| A | B | C=B/A | D | E | F=E/D | G | H | I=H/G | J | K | L=K/J | M | N | O=N/M | P | R | S=R/P | T | U | V=U/T | W | X | Y=X/W | Z=A+D+G+J+M+P+T+W | AA=B+E+H+K+N+R+U+X | AB=AA/Z
NP 2008/1 Further training of primary school teachers in the area of foreign languages in relation to the Policy of Foreign Language Education at Primary and Secondary Schools | 0 | 0 | 0% | 275152.6578 | 0 | 0% | 7527276.835 | 281994.51 | 3.746% | 6106841.367 | 5989154.37 | 98.07% | 1068655.2453 | 505010.73 | 47.26% | 1078638.7801 | 0 | 0 | 364715.3912 | 0 | 0% | 0 | 0 | 0% | 16421280.2764 | 6776159.61 | 41.26%
NP 2008/2 Further training of primary and secondary school teachers in the subject of informatics | 0 | 0 | 0% | 39319.86 | 0 | 0% | 5679992.56 | 67996.73 | 1.197% | 1719445 | 1758626.51 | 102.3% | 643420.73 | 315754.1 | 49.07% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 8082178.15 | 2142377.34 | 26.51%
NP 2008/3 Modernization of educational process at primary schools | 0 | 0 | 0% | 0 | 0 | 0% | 18445860.72 | 14108.8 | 0.07649% | 3810661.89 | 13191173.9 | 346.2% | 3628095.33 | 320876.58 | 8.844% | 3621456.55 | 0 | 0% | 3571212.57 | 0 | 0% | 0 | 0 | 0% | 33077287.06 | 13526159.28 | 40.89%
NP 2008/4 Modernization of educational process at secondary schools | 0 | 0 | 0% | 0 | 0 | 0% | 8315076.68 | 16713.41 | 0.201% | 1387505.81 | 5192967.66 | 374.3% | 1387505.81 | 152262.16 | 10.97% | 1387505.81 | 0 | 0% | 714155.54 | 0 | 0% | 0 | 0 | 0% | 13191749.65 | 5361943.23 | 40.65%
NP 2008/5 Teacher training in the creation of school education programmes | 0 | 0 | 0% | 0 | 0 | 0% | 1713024.79 | 0 | 0% | 1277153.02 | 329455.09 | 25.8% | 1277153.02 | 109036.87 | 8.537% | 1000360.67 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 5267691.61 | 438491.96 | 8.324%
NP 2008/7 Training of nursery school teachers as part of education reform | 0 | 0 | 0% | 0 | 0 | 0% | 9374 | 5630.8 | 60.07% | 3101017.86 | 5869035.5 | 189.3% | 3030000 | 351762.78 | 11.61% | 2271000 | 0 | 0% | 913603.46 | 0 | 0% | 0 | 0 | 0% | 18689621.32 | 6226429.08 | 33.31%
NP 2009/1 External school quality assessment in support of school self-assessment processes and development | 0 | 0 | 0% | 0 | 0 | 0% | 143126.48 | 0 | 0% | 233341.38 | 157822.87 | 67.64% | 172486.6 | 21828.89 | 12.66% | 263227.4 | 0 | 0% | 69101.65 | 0 | 0% | 0 | 0 | 0% | 881283.5 | 179651.76 | 20.39%
NP 2009/3 Professional and career growth of teaching staff | 0 | 0 | 0% | 0 | 0 | 0% | 1514094.66 | 0 | 0% | 22380850.8 | 175928.18 | 0.7861% | 9643468.54 | 212366.27 | 2.202% | 9056330.87 | 0 | 0% | 6089971.13 | 0 | 0% | 0 | 0 | 0% | 48684716 | 388294.45 | 0.7976%
NP 2010/1 Education quality evaluation at primary and secondary schools in the SR in the context of the current education reform | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 1850000 | 6295.57 | 0.3403% | 2800000 | 90294.14 | 3.225% | 2000000 | 0 | 0% | 298155 | 0 | 0% | 0 | 0 | 0% | 6948155 | 96589.71 | 1.39%
NP 2010/2 KomPrax - Competences for practice | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 2824942.96 | 12250.78 | 0.4337% | 2623385.16 | 0 | 0% | 2623385.15 | 0 | 0% | 0 | 0 | 0% | 8071713.27 | 12250.78 | 0.1518%
NP 2011/1 Through teacher training to social inclusion of marginalized Roma communities | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 4040663 | 0 | 0% | 8938490 | 0 | 0% | 6290196 | 0 | 0% | 5719653 | 0 | 0% | 24989002 | 0 | 0%
TOTAL | 0 | 0 | 0 | 314472.52 | 0 | 0 | 43347826.725 | 386444.25 | 0.8915% | 41866817.127 | 32670459.08 | 78.03% | 30516391.2353 | 2091443.3 | 6.854% | 32240395.2401 | 0 | 0 | 20934495.8912 | 0 | 0 | 5719653 | 0 | 0 | 184304677.8364 | 35148347.2 | 19.07%
Source: MA
*Financial data are for both goals (C+RCE), prematurely terminated NP are not included in Annex No. 8
**Annex No. 8 indicates drawing in relation to the Certification Authority (MF SR) within the actual drawing of NP as of 31 Dec.2011.