## MA
Annex 6
List of on-the-spot inspections performed by MA from 01 January 2013 - 31 December 2013
Ref. No. | Name of Beneficiary | Project name/ ITMS code | Place and time of the physical performance of the on-the-spot inspection | Amount of funding checked | Amount of funding checked as percentage of eligible project expenditures | Amount of ineligible expenditures identified | Principal findings, incl. any discrepancies | Corrective measures proposed for detected shortcomings | Results of adopted measures
1. | Institute of Information and Prognoses on Education | Modernisation of the education process at elementary schools / 26110130083 | Bratislava, 18/12/2012 - 11/04/2013 | N/A | N/A | N/A | 1. Discrepancy of dates: - The final work of an attendee was submitted before or on the assignment date of the final work. - The final work of an attendee was submitted with a delay (after the date on which the attendee was due to submit it). - The reviewer assessed the submitted final work before the date of its assignment - The deadline for the submission of the final work set by applying for the final exam (deadline for submission... ) precedes the date of assignment of the final work. 2. The protocol on the final exam is not signed by the member of the examination committee Ms. Rennerová (Mgr. Mária Baranová - 21718XFTGX, Mgr. Tomáš Blíž - 21961BVBLF) - The final work lacks the statutory declaration of the author about having written the final work on her own in line with the recommended literature (Mgr. Jana Andrijková - 21718XFTGX) | 1. Comply with the time and logical sequence when specifying dates. 2. Remedy the shortcoming and add the missing signatures in the protocols on the final exam and in one of the final works. | 1.N/A - Letter by the IIPE of 09 May 2013 2. Letter by the IIPE of 31 May 2013
2. | Institute of Information and Prognoses on Education | Modernisation of the education process at elementary schools / 26140130013 | Bratislava, 18/12/2012 - 11/04/2013 | N/A | N/A | N/A | 1. 1. Discrepancy of dates: - The final work of an attendee was submitted before the assignment date of the final work. - The final work of an attendee was submitted with a delay (after the date on which the attendee was due to submit it). - The deadline for the submission of the final work set by applying for the final exam (deadline for submission... ) precedes the date of assignment of the final work. | 1. Comply with the time and logical sequence when specifying dates. | 1. N/A - Letter by the IIPE of 09 May 2013
3. | Institute of Information and Prognoses on Education | Modernisation of the education process at secondary schools / 26110130084 | Bratislava, 18.12.2012 - 11.4.2013 | N/A | N/A | N/A | 1. 1. Discrepancy of dates: - The final work of an attendee was submitted before or on the assignment date of the final work. - The deadline for the submission of the final work precedes the date of assignment of the final work. - The final work of an attendee was submitted with a delay (after the date on which the attendee was due to submit it). 2. The following original documents were missing (copies of the documents were presented): - Opinion of the final work reviewer related to specialised studies (Ms. Katarína Blahútová, Ms. Miriam Feretová), - Statement of the author of the final work (Ms. Zuzana Džurdženíková, Ms. Daniela Filčáková, Mr. Jozef Cuper), - Statutory declaration of attendees about filling in all data required by the project also after the completion of education under the NP "Modernisation of the education process at secondary schools" (Ms. Zuzana Džurdženíková, Ms. Daniela Filčáková, Mr. Jozef Cuper). | 1. Comply with the time and logical sequence when specifying dates. 2. Doplniť chýbajúce dokumenty v originálnom vyhotovení. | 1. N/A - Letter by the IIPE of 09 May 2013 2. Letter by the IIPE of 31 May 2013
4. | Institute of Information and Prognoses on Education | Modernisation of the education process at secondary schools / 26140130014 | Bratislava, 18.12.2012 - 11.4.2013 | N/A | N/A | N/A | 1. 1. Discrepancy of dates: - The final work of an attendee was submitted before or on the assignment date of the final work. - The final work was submitted before the date of assignment of the final work. 2. The original copy of the "Statement of the author of the fianl work - consent to the publication of the final work" and of the about filling in all data required by the project also after the completion of education under the NP "Modernisation of the education process at secondary schools" were missing in the final work file of Ms. Júlia Schlarmannová. The copies of these documents were presented. | 1. Comply with the time and logical sequence when specifying dates. 2. Add missing documents in the original file. | 1. N/A - Letter by the IIPE of 09 May 2013 2. Letter by the IIPE of 31 May 2013
5. | Institute of Information and Prognoses on Education | Modern education - digital education for general education subjects / 26110130547 | Bratislava, 20/11/2013 - 20/11/2013 | N/A | N/A | N/A | No findings | Irrelevant | Irrelevant
6. | Institute of Information and Prognoses on Education | Higher education institutions as engines for the development of a knowledge-based society / 26110230089 | Bratislava, 26/11/2013 - 26/11/2013 | N/A | N/A | N/A | No findings | Irrelevant | Irrelevant
7. | National Institute for Education | Foreign language training for elementary school teachers / 26110130001 | Bratislava, 14/03/2013 - 25/06/2013 | 128610.55 | 1.3 | 2249.7 | Unjustified clearance of expenditure. Difference between the advance payment for salary and the clearance of expenditures. Failure to deal with computer technology and to hand it over to schools. Incomplete supporting documentation. | Complete the supporting documentation during the preparation of the request for payment in line with the Guidelines for Beneficiaries, version 7.0, Part 7.4. | Partly fulfilled
8. | National Institute for Education | Foreign language training for elementary school teachers / 26140130001 | Bratislava, 14/03/2013 - 25/06/2013 | 47847.17 | 6.37 | 21302.65 | Differences between the advance payment and the clearance of expenditures. Overlapping of expenditures for lecturers. Failure to verify the supporting documentation. Failure to hand over the computer technology to elementary schools. | Ensure elimination of the shortcomings described in the report. During the on-the-spot inspection of the elimination of shortcomings started on 28 January 2014, the MA identified new facts (related to the handing over of computer technology to schools) which will be included in the conclusions of the On-the-Spot Inspection Report. | Partly fulfilled
9. | State School Inspection | External evaluation of school quality supporting self-evaluation processes and school development / 26110130088 | Beatislava, 13/03/2013 | 10264.25 | 3.05 | 0 | No findings | Irrelevant | Irrelevant
10. | State School Inspection | External evaluation of school quality supporting self-evaluation processes and school development / 26140130018 | Beatislava, 13/03/2013 | 8554 | 13.67 | 14.05 | Discrepancy between work sheets and cumulative monthly work sheets. | Consistent filling in of work sheets and cumulative monthly work sheets. | Fulfilled
11. | National Institute for Certified Educational Measurements NUCEM | Increasing the quality of education at elementary schools and secondary schools using electronic testing / 26110130546 | Bratislava, 04/07/2013 | N/A | N/A | N/A | No findings | Irrelevant | Irrelevant
12. | National Institute for Certified Educational Measurements NUCEM | Increasing the quality of education at elementary schools and secondary schools using electronic testing / 26140130030 | Bratislava, 04/07/2013 | N/A | N/A | N/A | No findings | Irrelevant | Irrelevant
13. | Institute of Information and Prognoses on Education | Modernisation of the education process at elementary schools / 26110130083 | Bratislava, 18/12/2012 - 07/02/2013 | 16733.52 | 0.1 | 3.2 | Incorrect basis for the calculation of the amount of transfer payments. Discrepancy between attendance and the work sheet. | Consistently comply with Art. 9 of Act No. 502/2001 Coll. on Financial Control and Internal Audit as amended. | Fulfilled on 05 April 2013
14. | Institute of Information and Prognoses on Education | Modernisation of the education process at secondary schools / 26110130084 | Bratislava, 18/12/2012 - 07/02/2013 | 3632.33 | 0 | 0 | 1. Formal shortcomings in supporting documentation - item 7.5.3. Contribution to attendees. | 1. Consistently comply with Art. 9 of Act No. 502/2001 Coll. on Financial Control and Internal Audit as amended. Perform consistent formal control of the supporting documentation of staff executing the reimbursement of expenditures to schools under item 7.5.3. of the project budgets. | Fulfilled on 16 April 2013
15. | Institute of Information and Prognoses on Education | Modernisation of the education process at elementary schools / 26140130013 | Bratislava, 18/12/2012 - 07/02/2013 | 521.28 | 0.2 | 0 | No findings | Irrelevant | Irrelevant
16. | Institute of Information and Prognoses on Education | Modernisation of the education process at secondary schools / 26140130014 | Bratislava, 18/12/2012 - 07/02/2013 | 299.6 | 0.2 | 0 | 1. Formal shortcomings in supporting documentation - item 7.5.3. Contribution to attendees. | 1. Consistently comply with Art. 9 of Act No. 502/2001 Coll. on Financial Control and Internal Audit as amended. Perform consistent formal control of the supporting documentation of staff executing the reimbursement of expenditures to schools under item 7.5.3. of the project budgets. | Fulfilled on 16 April 2013
17. | State Institute of Vocational Education | Training for teachers with regard to the preparation of the School Education Programme / 26110130085 | Bratislava, 28/09/2012 - 09/05/2013 | 183257.41 | 9.25 | 0 | Findings without a financial impact | Ensure elimination of the shortcomings listed in the report. | Fulfilled, letter of 04 November 2013
18. | State Institute of Vocational Education | Training for teachers with regard to the preparation of the School Education Programme / 26140130015 | Bratislava, 28/09/2012 - 09/05/2013 | 7528.7 | 9.97 | 0 | Findings without a financial impact | Ensure elimination of the shortcomings listed in the report. | Fulfilled, letter of 04 November 2013
19. | Methodology and Pedagogy Centre | Training for the teaching staff of kindergartens / 26140130017 | Bratislava, 24/06/2013 - 24/06/2013 | N/A | N/A | N/A | No findings | Irrelevant | Irrelevant
20. | Methodology and Pedagogy Centre | Training for the teaching staff of kindergartens / 26110130087 | Bratislava, 10/01/2013 | N/A | N/A | N/A | No findings | Irrelevant | Irrelevant
21. | National Sports Centre | Increasing the qualification of teachers of physical and sports education / 26120130022 | Bratislava, 28/08/2013 | N/A | N/A | N/A | Control of actual performance of education activities and of compliance with publicity rules - no findings. | Irrelevant | Irrelevant
22. | Methodology and Pedagogy Centre | Training teaching staff for the inclusion of marginalised Roma communities / 26130130051 | Prešov, 14/01/2013 - 16/01/2013 | 216144.86 | 2.48 | 0 | No findings | Irrelevant | Irrelevant
23. | Methodology and Pedagogy Centre | Training teaching staff for the inclusion of marginalised Roma communities / 26130130051 | Prešov, 13/05/2013 - 17/05/2013 | 75348.76 | 0.86 | 561.73 | Overlapping of expenditures and discrepancy between the amount of claimed amount in SH and VL. | Continue in increased control activities, and consistently comply with the principles of economic management of public funds. | Informácia o splnení opatrení na nápravu nedostatkov a na odstránenie príčin ich vzniku zo dňa 27.6.2013
24. | Methodology and Pedagogy Centre | Training teaching staff for the inclusion of marginalised Roma communities / 26130130051 | Prešov, 10/06/2013 - 14/06/2013 | 101019.65 | 1.16 | 138.28 | Overlapping of time periods, discrepancy in works at VL and SH, failure to present supporting documentation, incorrect sum of work hours. | Continue in increased control activities, and consistently comply with the principles of economic management of public funds. | Informácia o splnení opatrení na nápravu nedostatkov a na odstránenie príčin ich vzniku zo dňa 26.7.2013
25. | Methodology and Pedagogy Centre | Training teaching staff for the inclusion of marginalised Roma communities / 26130130051 | Prešov, 05/08/2013 - 09/08/2013 | 103878.48 | 1.19 | 10.5 | Failure to prove the work performed in the supporting documentation. The beneficiary claims in the SH reimbursement higher than the justified claim according to the VL (transfers to health insurance company). | Continue in increased control activities, and consistently comply with the principles of economic management of public funds. | Informácia o splnení opatrení na nápravu nedostatkov a na odstránenie príčin ich vzniku zo dňa 22.8.2013
26. | National Institute for Certified Educational Measurements NUCEM | Evaluation of the quality of education at elementary schools and secondary schools in the context of the on-going contents reform of education / 26110130309 | Bratislava, 14/01/2013 - 30/01/2013 | 245583.5 | 10.96 | 341.28 | Control of work sheets - failure to comply with the Labour Code provisions; control of attendance sheets - number of participants to the computer training course. | No remedial measures | Irrelevant
27. | Methodology and Pedagogy Centre | Training teaching staff for the inclusion of marginalised Roma communities / 26130130051 | Prešov, 23/09/2013 - 27/09/2013 | 155664.89 | 1.78 | 1196.6 | Exceeding of the maximum admissible work time and of the unit price set in the budget. | Continue in increased control activities, and consistently comply with the principles of economic management of public funds. | Informácia o splnení opatrení na nápravu nedostatkov a na odstránenie príčin ich vzniku zo dňa 14. 10. 2013
28. | Methodology and Pedagogy Centre | Training teaching staff for the inclusion of marginalised Roma communities / 26130130051 | Prešov, 14/10/2013 - 22/10/2013 | 20784.65 | 0.24 | 217.31 | Exceeding of the maximum admissible work time and of the unit price set in the budget. | No remedial measures | Irrelevant
29. | Methodology and Pedagogy Centre | Training teaching staff for the inclusion of marginalised Roma communities / 26130130051 | Prešov, 25/11/2013 - 29/11/2013 | 44124.59 | 0.51 | 1344.21 | Exceeding of the maximum admissible work time and of the unit price set in the budget. | No remedial measures | Irrelevant
30. | IUVENTA - Slovak Youth Institute | KomPrax - Competences for practice / 26120130011 | Bratislava, 21/08/2013 | N/A | N/A | N/A | Upon arrival at the place of the training event, the inspection group found out that the training activity did not take place; another finding related to insufficient project publicity. | Consistently comply with the relevant information and publicity rules. | Fulfilled
31. | Ministry of Healthcare of the SR | PROJECT FOR THE USE OF TECHNICAL ASSISTANCE, I / 26150230002 | Bratislava, 19/11/2013 | 22964.88 | 1.932% | 0 | No findings | Irrelevant | Irrelevant
SOURCE: MA

## ASFEU
List of on-the-spot inspections performed by IB MA ASFEZ from 01 January 2013 - 31 December 2013
Ref. No. | Name of Beneficiary | Project name/ ITMS code | Place and time of the physical performance of the on-the-spot inspection | Amount of funding checked | Amount of funding checked as percentage of eligible project expenditures | Amount of ineligible expenditures identified | Principal findings, incl. any discrepancies | Corrective measures proposed for detected shortcomings | Results of adopted measures
1. | University of Trnava in Trnava, Hornopotočná 23, 918 43 Trnava | Innovative forms of education in the changing university education 26110230028 | Hornopotočná 23, 918 43 Trnava 23/01/2013 | 38 512,83 | 3.66 | 0 | No findings | Irrelevant | Irrelevant
2. | University of St. Cyril and Methodius in Trnava, Námestie J. Herdu 2, 917 01 Trnava | Preparation and application of e-learning courses at the Faculty of Massmedia Communication of the University of ss. Cyril and Methodius 26110230003 | Námestie J. Herdu 2 and Skladová 3, 917 01 Trnava 23/01/2013 | 49060.1 | 16.29 | 0 | No findings | Irrelevant | Irrelevant
3. | University of Constaine the Philosopher in Nitra, Tr. A. Hlinku 1, 949 01 Nitra | A-Centre of the Faculty of Natural Sciences of the University of Constantine the Philosopher in Nitra - Innovative Education Centre 26110230026 | Constantine the Philosopher University in Nitra, Tr. A. Hlinku 1, 949 01 Nitra 28/01/2013 | 24479.03 | 2.45 | 0 | No findings | Irrelevant | Irrelevant
4. | University of Constantine the Philosopher in Nitra, Tr. A. Hlinku 1, 949 74 Nitra | Preparation of the study programme for the inter-departmental study of massmedia studies and French using ICTs 26110230033 | Constantine the Philosopher University in Nitra, Tr. A. Hlinku 1, 949 74 Nitra 28/01/2013 | 35043 | 8.29 | 0 | No findings | Irrelevant | Irrelevant
5. | University of Žilina in Žilina, Univerzitná 8215/1, 010 26 Žilina | Systemisation of the transfer of advanced technologies and knowledge between the industrial sector and university environment 26110230004 | University of Žilina in Žilina, Univerzitná 8215/1, 010 26 Žilina 06/02/2013 | 68981.03 | 7.84 | 0 | No findings | Irrelevant | Irrelevant
6. | Slovak University of Technology in Bratislava, Vazovova 5, 812 43 Bratislava-Staré Mesto | Development of the teaching competencies of postgradual students at the Materials and Technology Faculty of the SUT 26110230023 | Slovak University of Technology in Bratislava, Vazovova 5, 812 43 Bratislava-Staré Mesto 13/02/2013 | 31347.5 | 8.26 | 0 | The control group found out that activity 1.2 Preparation and implemetnation of a post-gradual modular course was not implemented in full extent. The measurable project indicators have been fulfilled, but the subject of activity 1.2 has not. The funds used for activity 1.2 correspond to the current state of the activity. | It is proposed to implement activity 1.2 in full extent. The completion of activity 1.2 was delayed by 14 months on the basis of a Request for change of the Grant Contract received on 04 March 2013. Under this extended period, there is enough space to implement activity 1.2. | Irrelevant
7. | University of Prešov in Prešov, ul.17. novembra č.15, 080 01 Prešov | Opening the education space of the Universtiy of Prešov by creating a foreign language offer for e-learning study programmes 26110230030 | University of Prešov in Prešov, ul.17. novembra č.15, 080 01 Prešov 20/02/2013 | 171776.48 | 16.37 | 0 | No findings | Irrelevant | Irrelevant
8. | University of Veterinary Medicine and Pharmacy in Košice, Komenského 73, 041 81 Košice - Sever | New study and education programems at the University of Veterinary Medicine in Košice 26110230036 | University of Veterinary Medicine and Pharmacy in Košice, Komenského 73, 041 81 Košice - Sever 21/02/2013 | 77209.26 | 7.35 | 0 | No findings | Irrelevant | Irrelevant
9. | Matej Bel University in Banská Bystrica, Národná 12, 97401 Banská Bystrica | Development of the knowledge and teaching competencies of R&D staff and postgradual students at the Matej Bel University 26110230019 | Matej University in Banská Bystrica, Národná 12, 97401 Banská Bystrica 28/02/2013 | 38438.5 | 3.98 | 0 | No findings | Irrelevant | Irrelevant
10. | Institute of Physics of the Slovak Academy of Sciences, Dúbravská cesta 9, 845 11 Bratislava | Centre for the development of postgradual students. Education based on scientific knowledge. 26110230006 | Vrbovská cesta 110, 921 01 Piešťany, Dúbravská cesta 9, 845 11 Bratislava 07/03/2013 | 48853.18 | 15.08 | 0 | No findings | Irrelevant | Irrelevant
11. | Elementary school with a kindergarten Nálepkovo | Understanding words 26110130379 | Elementary School with a Kindergarten Nálepkovo, Školská 684, 053 33 Nálepkovo 12/03/2013 | Irrelevant | Irrelevant | Irrelevant | The project has not been implemented in line with the project timetable, and activity 3.1 has not been implemented. The Beneficiary failed to submit a request for for settlement of the advance or interim payment, and the documentation on the cash-flow and on the transfer of the advance payment has not been presented either. The documentation for the public procurement has not been submitted due to the incomplete public procurement process. | The Beneficiary was warned about its obligation to fully comply with the Grant Contract. The ASFEU required the submission of a detailed timetable of project activities for the next 12 months, the copies of cashflow referring to the transfer of the advance payment, and of a detailed plan of the use of funds for the next 12 months, and requests the completion of the public procurement process and the submission of the respective documentation for control. | Irrelevant
12. | Elementary school with a kindergarten, Komenského 2, Spišský Hrhov | Social inclusion of pupils through improvement of educaiton 26130130072 | Elementary School with a Kindergarten, Komenského 2, Spišský Hrhov, Komenského 2, 053 02 Spišský Hrhov 12/03/2013 | 39266.22 | 17 | 0 | No findings | Irrelevant | Irrelevant
13. | Municipality Bystrany, Bystrany 121, 053 62 Bystrany | Educating young Roma with incomplete primary education in Bystrany 26130130068 | Municipality of Bystrany 13/03/2013 | 30359.97 | 19.59 | 0 | No findings | Irrelevant | Irrelevant
14. | Re-education Centre, Prílepská 6, Zlaté Moravce | School of ideas and creativeness 26130230019 | Re-Education Centre, Prílepská 6, Zlaté Moravce 13/03/2013 | 32086.43 | 20.55 | 0 | No findings | Irrelevant | Irrelevant
15. | Municipality of Muráň, Muráň 329, 049 01 Muráň | Increasing the education level of the marginalised Roma community in the Municipality of Muráň 26130130086 | Municipality of Muráň 12/03/2013 | 646.4 | 0.72 | 0 | No findings | Irrelevant | Irrelevant
16. | Comenius University in Bratislava, Šafárikovo námestie 6, 818 06 Bratislava - Staré Mesto | Supporting human resources developmnet using state-of-the-art education processes and forms at the Jessenius Medical Faculty of the Comenius University in Martin 26110230031 | Malá Hora 10701/4A, 036 01, Martin 14/03/2013 | 16 283,88 | 1.56 | 0 | No findings | Irrelevant | Irrelevant
17. | Elementary School with a Kindergarten, Stráne pod Tatrami, District of Kežmarok | Reading for success 26130130073 | Slavkovská 19, Kežmarok 18/03/2013 | Irrelevant | Irrelevant | Irrelevant | The control group found out that no training of any of the two announced groups was carried out at the address specified in the notice. The access to the school building was closed, and there was no light in the building. | According to the control group´s finding, the beneficiary did not carry out the training according to its notice under activity 2.1 Enhancing teachers´ skills in the field of the preparation of teaching with an emphasis on reading literacy; training course: Development of meta-cognitive strategies - Group 1, and Development of meta-cognitive strategies, Group 2. The expenditure of 18 March 2013 for both groups within the course Development of meta-cognitive strategies was evaluated by the ASFEU as ineligible in full amount. | Irrelevant
18. | City University in Trenčín, Bezručova 64, 911 01 Trenčín | Introducing 1st grade study programme "Information system management" 26110230017 | City University in Trenčín, Bezručova 64, 911 01 Trenčín 19/03/2013 | 87985.01 | 8.64 | 0 | No findings | Irrelevant | Irrelevant
19. | ARISTO, s.r.o. | HERMES 26120130014 | ARISTO, s.r.o., Szakkayoho 1, Košice 19/03/2013 | 127610.07 | 34.94 | 0 | No findings | Irrelevant | Irrelevant
20. | HRCare, s.r.o., Námestie Slobody 60, 066 01 Humenné | Through innovative education towards increased competitiveness of building companies and further education lecturers 26120130007 | Štefániková 4, 071 01 Michalovce 20.03.2013 | 38616.8 | 7.83 | 0 | No findings | Irrelevant | Irrelevant
21. | SLCP Consulting , s.r.o., Univerzitná 8413/6, 010 08 Žilina | Increasing the competitiveness of Slovak manufacturing by improving the effectiveness of corporate processes and innovation efficiency 26120130003 | Askoll Slovakia s. r. o., 916 25 Potvorice 331 21/03/2013 | Irrelevant | Irrelevant | Irrelevant | No findings | Irrelevant | Irrelevant
22. | Elementary School, Školská 281, Brodské, Školská 281, 908 85 Brodské | From elementary literacy towards an information society and competitiveness 26110130404 | Elementary School, Školská 281, 908 85 Brodské 27/03/2013 | 41299.2 | 14.35 | 0 | No findings | Irrelevant | Irrelevant
23. | Elementary School, Ul.1Mája 12, 069 01 Snina | With sports and modern education towards the new Europe 26110130419 | Elementary School, Ul.1, Mája 12, 069 01 Snina 21/05/2013 | 14665.08 | 3.79 | 14665.08 | The technology was not installed, as a result of which its use could not be verified under the Grant Contract, and the objectives of the activities could not be fulfilled to the extent stipulated in the Grant Contract. | Ineligible expenditure of EUR 14,665.08 under Grant Contract No. 26110130419209. | Irrelevant
24. | Elementary School of Hana Zelinová Vrútky, Čachovská rad 34, 036 01 Vrútky | ZELINNOVA - Innovations in education at Hana Zelinová Elementary School in Vrútky 26110130386 | Elementary School of Hana Zelinová Vrútky, Čachovská rad 34, 036 01 Vrútky 07/05/2013 | 10575.08 | 2.64 | 0 | The Beneficiary did not account for the accounting operations in line with the Notice of Payment under items 11T1 and 11T2, but under items set by the school founder. The Beneficiary was reminded about this shortcoming and is due to take remedial measures. Another shortcoming identified was the incorrect filling in of Monitoring Report No. 2 (wrong data on the fulfilment of measurable indicators). The control group also identified incorrect arrangement of the supporting documentation to the request for payment. | After correcting the funds items, the Beneficiary will send a statement from the general ledger and from the journal by 15 June 2013. The Beneficiary will correct the wrong data in the Monitoring Report No. 2 and will submit it to the ASFEU upon the Call for Correction and/or Completion of the Monitoring Report within the set deadline. After being warned on site, the Beneficiary correctly arranged the supporting documentation of the request for payment. | On 14 June 2013, the Beneficiary delivered the statement from the general ledger and from the journal with correct accounting of the given item. The Beneficiary stated correct data on the fulfilment of measurable indicators in Monitoring Report No. 2. The MR was approved on 23 May 2013. The Beneficiary managed to correctly arrange the supporting documentation for the request on payment on the spot.
25. | Elementary School of Zoltána Kodálya with Hungarian as the language of instruction - Kodály Zoltán Alapiskola, Švermova 8, 924 00 Galanta - Galánta | Digital education for pupils from Zoltán Kodály Elementary School with Hungarian as the language of instruction 26110130444 | Elementary School of Zoltán Kodály with Hungarian as the language of instruction, Švermova 8, 924 00 Galanta 16/04/2013 | 22643.98 | 12.09 | 0 | The Beneficiary failed to present the project accounts – statements from the general ledger and from the journal. The Beneficiary was reminded to keep the accounts under analytical records in line with the Contract and to keep the expenditure according to the sources of financing (ESF funds – 85 %, state budget funds aimed for co-financing – 10%, and Beneficiary´s own funds – 5%). The Beneficiary was repeatedly reminded about the need to comply with the financial management rules – to transfer the advance payment to the founder. Upon physical verification, the control group found out incompliance between the serial numbers of assets (31 pcs of Toshiba Satellite C850 laptops – 138 B9502.1G15,6w7) and inventory numbers stated in the Assets List No. 23 (Ref. no. 1 – 31). | To bring the inventory numbers into compliance with serial numbers and with the List of Assets No. 13, and send the photocopy of the list to the ASFEU within 10 days from the delivery of the On-the-Spot Inspection Report. | The Beneficiary presented the required accounts – the accounting for the advance payment with ITMS code 26110130444 101 for two types funds (EU and SB) and the accounting for the supplier invoice no. 121174 for three types of funds (EU, SB, own funds). The Beneficiary documented the accounting operations in the journal, and submitted (on 31 May 2013) a photocopy of the documents with complying inventory and serial numbers and the List of Assets.
26. | Dubnický technologický inštitút, s. r. o., Dukelská štvrť 1404/613, 018 41 Dubnica nad Váhom | Virtual university: improving the external form of study at the Technology Institute of Dubnica 26110230010 | Dubnický technologický inštitút, s. r. o., Dukelská štvrť 1404/613, 018 41 Dubnica nad Váhom 02/05/2013 | 211812.19 | 20.14 | 0 | No findings | Irrelevant | Irrelevant
27. | University of St. Cyril and Methodius in Trnava, Nám. J. Herdu 2, 917 01 Trnava | Applied ethics for a knowledge-based society 26110230002 | Námestie J. Herdu 2 and Skladová 3, 917 01 Trnava 21/05/2013 | 11065.18 | 2.99 | 0 | No findings | Irrelevant | Irrelevant
28. | Pavol Jozef Šafárik University in Košice, Šrobárova 2, 041 80 Košice | Modernisation of postgradual study programmes in natural sciences and humanities at UPJS (DOKTORAND) 26110230013 | Pavol Jozef Šafárik University in Košice, Šrobárova 2, 041 80 Košice 05/06/2013 | 21 243,94 | 2.06 | 0 | No findings | Irrelevant | Irrelevant
29. | Pavol Jozef Šafárik University in Košice, Šrobárova 2, 041 80 Košice | Modern public administration - Preparation and innovation of study programmes of the Faculty of Public Administration of UPJS (MoVeS) 26110230038 | Pavol Jozef Šafárik University in Košice, Šrobárova 2, 041 80 Košice 06/06/2013 | 8747.32 | 1.48 | 0 | No findings | Irrelevant | Irrelevant
30. | GKTI, s.r.o., Štefániková 45/A, 921 01, Piešťany | 3K for tourism 26120130019 | GKTI, Štefániková 45, 921 01 Piešťany/Penzión Diana, Matuškova 21, 921 01 Piešťany 07/06/2013 | Irrelevant | Irrelevant | Irrelevant | No findings | Irrelevant | Irrelevant
31. | Joint Evangelical School, Komenského 10, 031 01 Liptovský Mikuláš | Using modern technology towards better understanding 26110130375 | Joint Evangelical School, Komenského 10, Hurbanova 6,031 01 Liptovský Mikuláš 27/05/2013 | 12 062,48 | 4.43 | 0 | The Beneficiary failed to comply with the Grant Contract, having kept incorrect accounts from the date of receipt of the first advance payment on 23 July 2012 until the day of inspection on 27 May 2013. The respective items were accounted for analytical accounts at an incorrect proportion of the sources of financing (ESF funds – 85%, state budget funds – 10%, and Beneficiary´s own funds – 5%). The Beneficiary failed to break down the wage funds into three types of resources, and to account the accounting operations in line with the Payment Notice under items 11T1 and 11T2. The control group found out that some didactic tools (see Annex 1 to the On-the Spot Inspection Report – claim letters) stated in the invoice were physically missing. The Beneficiary supported the missing didactic tools with claim letters of 04 April 2013 and 07 May 2013, which were taken over by the representatives of the MIVASOFT spol. s.r.o. company. | The Beneficiary was reminded to keep its accounts under analytical records in line with the Contract, to keep all expenditure at the correct proportion of the sources of financing (ESF funds – 80.75%, state budget funds aimed for co-financing – 14.25%, and Beneficiary´s own funds – 5%), and to account the accounting operations in line with the Payment Notice under items 11T1 and 11T2. The Beneficiary was also requested to ensure correct accounting of the accounting items of 2013 and to present a statement from the general ledger and from the journal. Deadline: within 14 days from the delivery of the On-the-Spot Inspection Report Inform the ASFEU about the settlement of the claim and about the delivery of claimed items. Present a photo-documentation of the didactic tools. Deadline: within 7 days from the settlement of the claim. | The Beneficiary complied with the measure within the set deadline.
32. | Joint School, Letná ulica 3453/34, 058 01 Poprad | Meeting the challenges of modern school: Text as a communication medium and a universal tool for education in the 3rd millennium 26110130392 | Joint School, Letná ulica 3453/34, 058 01 Poprad 28/05/2013 | 47 886,00 | 16.1 | 0 | No findings | Irrelevant | Irrelevant
33. | Elementary School, Hviezdoslavova 822/8, 028 01 Trstená | Modernisation of the education process at Elementary School Trstená 26110130396 | Elementary School, Hviezdoslavova 822/8, 028 01 Trstená, 22/05/2013 | 3858.69 | 1.55 | 0 | Due to the incomplete public procurement process, the Beneficiary is not expected to comply with the schedule of follow-up activities. | The ASFEU requests the Beneficiary to complete the public procurement process and to submit the respective documentation for control. Deadline: within 15 calendar days from the delivery of the On-the-Spot Inspection Report. | The Beneficiary complied with the measure within the set deadline.
34. | Elementary School with a Kindergarten, Školská 49, Žilina, Školská 19, 010 04 Žilina | Our school in Závodie for all 26110130451 | Elementary School with a Kindergarten, Školská 49, 010 04 Žilina 21/05/2013 | 9087.08 | 4.89 | 0 | No findings | Irrelevant | Irrelevant
35. | Elementary School of Rudolf Dilong, Hviezdoslavova 823/7, 028 01 Trstená | Supporting school in the Region of Orava in innovative teaching 26110130397 | Elementary School of Rudolf Dilong, Hviezdoslavova 823/7, 028 01 Trstená 22/05/2013 | 18 850,53 | 8.86 | 0 | The control group found out that the Beneficiary kept accounting under synthetic and analytical records, having accounted for all project-related expenditure by sources of financing, but at an incorrect proportion. Since it is a church school, the proportion of funds on the basis of the Grant Contract is 80.75% for ESF funds, 14.25% for state budget funds, and 5% for own funds. | Correct the accounting of items concerning the project of 2013, and document their correct accounting – present statements from the general ledger and from the journal (Annex 1). Deadline: 15 July 2013. | The Beneficiary complied with the measure within the set deadline.
36. | Elementary School, Slovenských dobrovoľníkov 122/7, 010 03 Žilina | Education for better life 26110130399 | Elementary School, Slovenských dobrovoľníkov 122/7, 010 03 Žilina 21/05/2013 | 23 242,77 | 13.04 | 0 | The control group could not check the camera Canon PowerShot SX40 HS + 8GB SD card, inventory no. 10682, because the camera was taken by the teachers to the excursion to London under activity 1.1 Modern English language teaching at the 2nd grade of elementary schools. | The camera Canon PowerShot SX40 HS could not be physically checked for the aforementioned reasons. After return from the excursion, the Beneficiary is requested to present to the ASFEU the photo-documentation concerning the camera. Deadline: 14 days after the delivery of the On-the-Spot Inspection Report. | The Beneficiary complied with the measure within the set deadline.
37. | Catholic University in Ružomberok, Námestie Andreja Hlinku 60, 034 01 Ružomberok | Supporting the professional growth of postgraduate students and improving the conditions of postgraduate studies at the Faculty of Pedagogy in Ružomberok 26110230015 | Catholic University in Ružomberok 15/05/2013 | 38 366,54 | 9.35 | 0 | No findings | Irrelevant | Irrelevant
38. | Elementary School, Mičurova 364/1 , Bytča, 014 01 | Discovering new paths in education 26110130400 | Elementary School, Mičurova 364/1 , Bytča, 014 01 29/04/2013 | 51840.5 | 32.86 | 0 | No findings | Irrelevant | Irrelevant
39. | SEVŠ Skalica | Improving the quality of higher education at SEVŠ in Skalica in the Environmental Management study programme 26110230046 | Kráľovská 386/11, 909 01 Skalica 15/05/2013 | 180697.1 | 38.79 | 0 | No findings | Irrelevant | Irrelevant
40. | University of Prešov in Prešov, ul. 17. novembra č.15, 080 01 Prešov | University modernsation and improved management 26110230032 | Ul. 17 novembra 15, 080 01 Prešov 06/06/2013 | 327 470,83 | 31.16 | 0 | No findings | Irrelevant | Irrelevant
41. | Matej Bel University in Banská Bystrica, Národná 12, 974 01 Banská Bystrica | Increasing the quality of management and higher education 26110230021 | Národná 12, 974 01 Banská Bystrica; Cesta na amfiteáter 1, 974 01 Banská Bystrica 29/05/2013 | 27840.65 | 7.23 | 0 | No findings | Irrelevant | Irrelevant
42. | Elementary School with a Kindergarten, Mikušovce 16, Mikušovce 16, 018 57 Mikušovce | Modernisation of education - the precondition for the future success of pupils 26110130486 | Elementary School with a Kindergarten, Mikušovce 16, 018 57 Mikušovce 10/06/2013 | irelevatné | irelevatné | irelevatné | No findings | Irrelevant | Irrelevant
43. | Institute of Experimental Physics of SAS Košice | Educational Centre of Physics of UEF SAV 26110230034 | Watsonova 47, 040 01 Košice - Sever 06/06/2013 | 22054.96 | 3.58 | 0 | No findings | Irrelevant | Irrelevant
44. | University of Trnava in Trnava, Hornopotočná 23, 918 43 Trnava | Improving the effectiveness of the university administration and management using modern technology 26110230027 | University of Trnava in Trnava, Hornopotočná 23, 918 43 Trnava 16/04/2013 | 28406.2 | 2.84 | 0 | No findings | Irrelevant | Irrelevant
45. | Pavol Jozef Šafárik University in Košice, Šrobárova 2, 041 80 Košice | Modern and interactive education at UPJS 26110230035 | Pavol Jozef Šafárik University in Košice, Šrobárova 2, 041 80 Košice 05/06/2013 | 39698.93 | 3.8 | 0 | No findings | Irrelevant | Irrelevant
46. | Constantine the Philosopher University in Nitra, Trieda Andreja Hlinku 1, 949 74 Nitra | Internal quality assurance of education at the Constantine the Philospher University in Nitra through the implementation of European norms and standards (ESG) 26110230050 | Constantine the Philosopher University in Nitra, Trieda Andreja Hlinku 1, 949 74 Nitra 15/05/2013 | 26061.52 | 4.48 | 0 | No findings | Irrelevant | Irrelevant
47. | Constantine the Philosopher University in Nitra, Trieda Andreja Hlinku 1, 949 74 Nitra | Evaluation of research quality at the Constantine the Philosopher University in Nitra 26110230041 | Constantine the Philosopher University in Nitra, Trieda Andreja Hlinku 1, 949 74 Nitra 19/06/2013 | 26 285,27 | 4.73 | 0 | No findings | Irrelevant | Irrelevant
48. | Constantine the Philosopher University in Nitra, Trieda Andreja Hlinku 1, 949 74 Nitra | Education through theatre 26110230022 | Constantine the Philosopher University in Nitra, Trieda Andreja Hlinku 1, 949 74 Nitra 19/06/2013 | 43390.93 | 5.2 | 0 | No findings | Irrelevant | Irrelevant
49. | Comenius University in Bratislava, Šafárikovo nám. 6, 818 06 Bratislava - Staré Mesto | Comprehensive system of quality assessment of the teaching process and R&D work at the Jessenius Medical Faculty of the CU in Martin 26110230040 | Malá Hora 10701/4A, 03601 Martin 08/08/2013 | 39089.89 | 6.36 | 0 | No findings | Irrelevant | Irrelevant
50. | University of Žilina in Žilina, Univerzitná 8215/1, 010 26 Žilina | Developing a culture of quality at the University of Žilina on the basis of European higher education standards 26110230060 | Univerzitná 8215/1, 010 26 Žilina 14/08/2013 | 27292.28 | 4.34 | 0 | No findings | Irrelevant | Irrelevant
51. | University of Žilina in Žilina, Univerzitná 8215/1, 010 26 Žilina | Human resources development with the support of an integrated information system for the assessment of R&D results 26110230063 | Univerzitná 8215/1, 010 26 Žilina 14/08/2013 | 28709.5 | 6.51 | 0 | No findings | Irrelevant | Irrelevant
52. | Elementary School with a Kindergarten, SNP 412, Stakčín, SNP 412, 067 61 Stakčín | We´ll not learn about modern things in a non-modern way 26110130485 | SNP 412, Stakčín, SNP 412, 067 61 Stakčín 22/08/2013 | Irrelevant | Irrelevant | 0 | No findings | Irrelevant | Irrelevant
53. | Elementary School, Ul. 1. mája 12, 069 01 Snina | With sports and modern education towards new Europe 26110130419 | Ul. 1. mája 12, 069 01 Snina 23/08/2013 | Irrelevant | Irrelevant | 0 | No findings | Irrelevant | Irrelevant
54. | University of Technology in Zvolen, T. G. Masaryka 24, 960 53 Zvolen | Creation of study programmes in a world language, and support for foreign language teaching at the University of Technology in Zvolen 26110230037 | T. G. Masaryka 20, T. G. Masaryka 24, 960 53 Zvolen 03/09/2013 | 58035.86 | 5.51 | 0 | No findings | Irrelevant | Irrelevant
55. | Institute of Experimental Physics of the SAS, Watsonov 47, 040 01 Košice - Sever | Education Centre for the Research and Development of Complex Nano_Systems ("ECVV-NANOKOP") 26110230061 | Watsonov 47, 040 01 Košice - Sever 04/09/2013 | 59335.8 | 9.91 | 0 | No findings | Irrelevant | Irrelevant
56. | Dubnický technologický inštitút s.r.o., Dukelská štvrť 1404/613, 018 41 Dubnica nad Váhom | Increasing the quality of education and human resources development in the Technological Institute of Dubnica 26110230059 | Sládkovičova 533/20, 018 41 Dubnica nad Váhom 05/09/2013 | 97453.8 | 16.44 | 0 | No findings | Irrelevant | Irrelevant
57. | Elementary School of Bartolomej Krpelec, Tarasa Ševčenka 3, 085 055 Bardejov | Implementation of innovative education methods 26110130420 | Tarasa Ševčenka 3, 085 055 Bardejov 10/09/2013 | 48419.92 | 13.97 | 0 | No findings | Irrelevant | Irrelevant
58. | Elementary School, Nám.arm.genwerála L.Svobodu 16, 085 01 Bardejov | Enhancing the key competences of pupils through innovation of education 26110130391 | Nám. arm. generála L. Svobodu 16, 085 01 Bardejov 11/09/2013 | 38651.09 | 17.95 | 0 | No findings | Irrelevant | Irrelevant
59. | University of Trnava in Trnava, Hornopotočná 23, 918 43 Trnava | Rationalisation of education at the University of Trnava 26110230039 | Hornopotočná 23, Trnava 11/09/2013 | 52431.17 | 9.75 | 0 | No findings | Irrelevant | Irrelevant
60. | Catholic University in Ružomberok, Námestie Andreja Hlinku 60, 034 01 Ružomberok | Improving the quality of education, research and management system at the Catholic University in Ružomberok 26110230044 | Námestie Andreja Hlinku 60, 034 01 Ružomberok 11/09/2013 | 65730.81 | 12.94 | 0 | No findings | Irrelevant | Irrelevant
61. | Elementary School of Hana Zelinová, Čachovský rad 34, 036 01 Vrútky | ZELINNOVA - Innovation of education at Hana Zelinová Elementary School in Vrútky 26110130386 | Čachovský rad 34, 036 01 Vrútky 12/09/2013 | Irrelevant | Irrelevant | 0 | According to the notice on the training activity of 12 September 2013, the planned number of training participants was 4, and the number of lecturers 1. Three participants were physically present at the training (one of them took a leave), as well as one lecturer. | Justify the absence of the participant at the training and present a document proving the leave; otherwise, the expenditure for the lecturer will be reduced given the number of participants to the training. Deadline: 25 October 2013 | The Beneficiary justified the absence of the participant at the training.
62. | Elementary School in Giraltovce, Budovateľská 164/4, 087 01 Giraltovce | Modernisation of the content and methods of education 26110130383 | Budovateľská 164/4, 087 01 Giraltovce 17/09/2013 | 63715.8 | 23.78 | 0 | No findings | Irrelevant | Irrelevant
63. | Elementary School, Komenského 6, 064 01 Stará Ľubovňa | Thanks to reading we know more 26110130390 | Komenského 6, 064 01 Stará Ľubovňa 17/09/2013 | 43196.69 | 21.01 | 0 | No findings | Irrelevant | Irrelevant
64. | Elementary School with a Kindergarten Podolínec, Školská 2, 065 03 Podolínec | Experiential learning 26110130408 | Školská 2, 065 03 Podolínec 18/09/2013 | 25722.35 | 12.09 | 0 | No findings | Irrelevant | Irrelevant
65. | Elementary School, Prostějovská 38, 080 01 Prešov | Interactive school for all children 26110130401 | Prostějovská 38, 080 01 Prešov 18/09/2013 | 9825.3 | 5.68 | 0 | The assets that were in the school building at the time of the control were not marked with filing numbers. The goods were delivered shortly before the on-the-spot inspection and the Beneficiary had not time to mark all assets with labels. | The Beneficiary will send via e-mail the scanned version of the “Inventory of acquired assets” with expenditure concerning the delivered goods within ten days from the receipt of the On-the-Spot Control Report. | The Beneficiary presented the “Inventory of acquired assets” on time, stating the expenditure of the delivered goods.
66. | Elementary School of Pavol Emanuel Dobšinský, Slavošovce 125, 049 36 Slavošovce | Let´s be successful 26130130071 | Slavošovce 125, Slavošovce 125, 049 36 Slavošovce 18/09/2013 | 27403.14 | 23.87 | 0 | No findings | Irrelevant | Irrelevant
67. | Elementary School Zámutov, Zámutov 531, 094 15 Zámutov | Innovative education as a tool for the inclusion of MRCs into the learning process and into society 26130130075 | Zámutov 531, 094 15 Zámutov 19/09/2013 | 63924.43 | 29.45 | 0 | No findings | Irrelevant | Irrelevant
68. | Special Elementary School, M.R. Štefánika 83, 075 01 Trebišov | Learning about the world through reading 26130130053 | M.R. Štefánika 83, 075 01 Trebišov 19/09/2013 | 14654.21 | 9.2 | 0 | No findings | Irrelevant | Irrelevant
69. | Constantine the Philosopher University in Nitra, Trieda Andreja Hlinku 1, 949 74 Nitra | Imrpoving the quality of training for psychologists in line with the requirements of the European Certificate on Psychology 26110230043 | Kraskova 1, 949 74 Nitra 23/09/2013 | 46574.2 | 10.68 | 0 | No findings | Irrelevant | Irrelevant
70. | Slovak University of Agriculture in Nitra, Trieda Andreja Hlinku 2, 949 76 Nitra | Improving the quality of education at the SUA in Nitra and its adaptation to the current and prospective needs of the society 26110230057 | Trieda Andreja Hlinku 2, 949 76 Nitra 23/09/2013 | 31581.18 | 5.9 | 0 | No findings | Irrelevant | Irrelevant
71. | Elementary School with a Kindergarten of St. Marko Križin, Rehoľná 2, 040 18 Košice - Krásna | Innovaiton of education in the Elementary School of Sr. Marko Križina with a Kindergarten 26110130434 | Rehoľná 2, 040 18 Košice - Krásna 24/09/2013 | 16151.45 | 12.45 | 0 | No findings | Irrelevant | Irrelevant
72. | University of Prešov of Prešov, Ul. 17. novembra 15, 080 01 Prešov | Improving the quality of education at the University of Prešov 26110230048 | Ul. 17. novembra 15, 080 01 Prešov 24/09/2013 | 27233.05 | 4.77 | 0 | No findings | Irrelevant | Irrelevant
73. | Elementary School, Polianska 1, 040 01 Košice | Welcome to the knowledge-based society! 26110130415 | Polianska 1, 040 01 Košice 25/09/2013 | 54011.35 | 20.54 | 0 | No findings | Irrelevant | Irrelevant
74. | Grammar School, Hurbanova 34, 982 01 Tornaľa | Modernisation of education for success on the labour market 26110130542 | Hurbanova 34, 982 01 Tornaľa 02/10/2013 | Irrelevant | Irrelevant | 0 | 1) It was not possible to check the accounting of advance payment no. 26110130542 101 broken down by sources of financing (EU funds, state budget funds, own funds) according to the Paying Unit´s notice, since the Beneficiary failed to present the relevant documents. 2) It was not possible to assess the progress of activities 2.1 Modernisation of the education process and 3.1 Increasing the qualification of teaching staff, as the Beneficiary failed to present any outputs, work sheets or other relevant documentation on the activities. The justification of the Beneficiary suggests that the activities cannot be successfully executed due to the on-going inspection of the documentation on the public procurement of methodological, peer-review and consultation services in the ASFEU, and due to the incomplete analysis of the current condition of the school as an output of activity 1.1. This analysis is expected to form the basis for the creation and innovation of curricula under activity 2.1 and for the implementation of the education process under activity 3.1. The public procurement plan 2013 suggests that the public procurements of equipment, didactic tools and training for teaching staff were not carried out in line with the schedule. The Beneficiary prepared a new public procurement plan for 2013 (delivered on 18 October 2013), setting out new dates for executing the public procurement of equipment, didactic tools and training for teaching staff. | 1) The Beneficiary is requested to present the breakdown of the advance payment 26110130542 101 by sources of financing in line with the Paying Unit´s notice in verifiable form. Deadline: by 15 January 2014. 2) The implementation of activity 1.1 Analysis of the current condition of the school will be extended by 12/2013 on the basis of Amendment 1 to the Contract. The Beneficiary will also execute the remaining public procurements in 2013. The Beneficiary is obliged to send to the ASFEU the documentation on the public procurement of equipment, didactic tools and training for teaching staff for inspection. Deadline: by the end of 2014 | Irrelevant as of 31 December 2013.
75. | Special Elementary School, Odborárska 2 Košice, Odborárska 2, 040 01 Košice - Sever | Increasing the education level of pupils from MRCs 26130130056 | Odborárska 2, 040 01 Košice - Sever 03/10/2013 | 54222.57 | 26.52 | 0 | No findings | Irrelevant | Irrelevant
76. | Elementary School, Obchodná 5, 078 01 Sečovce | Innovation of education methods at Elementary School Obchodná 26110130427 | Obchodná 5, 078 01 Sečovce 08/10/2013 | 69547.96 | 33.42 | 0 | No findings | Irrelevant | Irrelevant
77. | Special Elementary School, Tichá 50, 072 04 Trhovište | I won´t be get lost in life 26110130447 | Tichá 50, 072 04 Trhovište 08/10/2013 | 41546.75 | 19.16 | 0 | No findings | Irrelevant | Irrelevant
78. | Pavol Horov Elementary School Michalovce, Kpt. Nálepku 16, 071 01 Michalovce | Innovation and digitisation of selected subjects with an emphasis on English language and reading literacy at Pavol Horov Elementary School in Michalovce 26110130443 | Kpt. Nálepku 16, 071 01 Michalovce 09/10/2013 | 10947.92 | 3.81 | 0 | No findings | Irrelevant | Irrelevant
79. | Elementary School, T. J. Moussona 4, 071 01 Michalovce | The gate to knowledge is open 26110130425 | T. J. Moussona 4, 071 01 Michalovce 09/10/2013 | 37658.91 | 21.45 | 0 | No findings | Irrelevant | Irrelevant
80. | Elementary School, Báb 225, 951 34 Báb | Reading literacy and English for pupils as a solid basis for achieving future objectives 26110130394 | Báb 225, 951 34 Báb 10/10/2013 | 44255.48 | 22.56 | 0 | No findings | Irrelevant | Irrelevant
81. | Elementary School, Drábova 3, 040 23 Košice | Modern school - the basis for a successful life of individuals 26110130456 | Drábova 3, 040 23 Košice 15/10/2013 | 67453.97 | 44.5 | 0 | No findings | Irrelevant | Irrelevant
82. | Elementary School, Zimná ulica 190, 049 25 Dobšiná | School of modern education 26130130081 | Zimná ulica 190, 049 25 Dobšiná 15/10/2013 | 24480.09 | 14.01 | 0 | No findings | Irrelevant | Irrelevant
83. | Elementary School, of Juro Hronec, Zakarpatská 12, 048 01 Rožňava | Enhancing the understanding of texts and education in English language towards an open Europe 26110130373 | Zakarpatská 12, 048 01 Rožňava 16/10/2013 | 46412.96 | 12.84 | 0 | No findings | Irrelevant | Irrelevant
84. | Elementary School of Arnold Ipolyi with Hungarian as the language of instruction, Hlavná 294, Balog nad Ipľom - Ipolybalog | Educate the new generation in a modern way 26110130483 | Hlavná 294, Balog nad Ipľom - Ipolybalog 16/10/2013 | 25026.13 | 14.01 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013
85. | Elementary School with a Kindergarten Bušince, Bušince, PSČ 991 22 | Transforming the Elementary School Bušince from traditional school to a modern one 26110130439 | Krtíšska 26, Bušince 17/10/2013 | 46202.56 | 13.77 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013
86. | Elementary School, Kukučínova 106, 093 03 Vranov nad Topľou | Better life through enhanced reading 26130130079 | Kukučínova 106, 093 03 Vranov nad Topľou 22/10/2013 | 20075.28 | 7.24 | 0 | No findings | Irrelevant | Irrelevant
87. | Elementary School, Ľ. Podjavorinskej 1, 040 11 Košice - Západ | Increasing the education level of members of marginalised Roma communities 26130130057 | Ľ. Podjavorinskej 1, 040 11 Košice - Západ 22/10/2013 | 28129.01 | 16.25 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013
88. | Elementary School Krajná Poľana, Krajná Poľana 36, 090 05 Krajná Poľana | Modern educaiton for pupils from MRCs from the Elementary School in Krajná Poľana 26130130062 | Krajná Poľana 36, 090 05 Krajná Poľana 23/10/2013 | 81638.47 | 25.94 | 0 | No findings | Irrelevant | Irrelevant
89. | University of Veterinary Medicine and Pharmacy in Košice, Komenského 73, 041 80 Košice – Sever | The University of Veterinary Medicine and Pharmacy in Košice is increasing the quality of its education 26110230064 | Komenského 73, 041 81 Košice - Sever 23/10/2013 | 167084.99 | 29.55 | 0 | The delay of results of activity 1.2 has an impact on the implementation of activity 1.4, which causes incompliance with the schedule of project activities. | The Beneficiary is currently preparing a request for change in the contract asking for extension of the deadline for the implementation of activity 1.4. and of the project duration. | Irrelevant
90. | University of Žilina in Žilina, Univerzitná 8215/1, 010 26 Žilina | Increasing the competitiveness of technical study programmes reflecting the current needs of the business practice 26110230052 | Univerzitná 8215/1, 010 26 Žilina 23/10/2013 | 3446.66 | 0.55 | 0 | No findings | Irrelevant | Irrelevant
91. | Institute of Parasitology of the Slovak Academy of Sciences, Hlinkova 3, 040 01 Košice - Sever | Research and educatio Centre for Parasitology of the SAS 26110230045 | Hlinkova 3, 040 01 Košice – Sever 23/10/2013 | 44636.54 | 7.99 | 0 | No findings | Irrelevant | Irrelevant
92. | Elementary School, Pionierska 33, Čaňa, Pionierska 33, 044 14 Čaňa | Modern school in the 21st century 26110130488 | Pionierska 33, 044 14 Čaňa 24/10/2013 | 71031.3 | 19.08 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013
93. | Security Management College in Košice, Kukučínova 17, 040 01 Košice | Improving and innovating the content and forms of education in the study programme Security Systems Management 26110230053 | Kukučínova 17 and Košťova 01, 040 01 Košice – Juh 24/10/2013 | 271789.77 | 43.16 | 0 | No findings | Irrelevant | Irrelevant
94. | Pavol Jozef Šafárik University in Košice, Šrobárova 2, 041 80 Košice | Research and education at UPJS - towards excellent European universities (EXPERT) 26110230056 | Šrobárova 2, 041 80 Košice 24/10/2013 | 41106.32 | 6.59 | 0 | No findings | Irrelevant | Irrelevant
95. | Elementary School, ul. Duchnovičova 480/29, 068 01 Medzilaborce | Enhnacing key competencies in a modern school 26110130405 | Duchnovičova 480/29, 068 01 Medzilaborce 29/10/2013 | 54465.35 | 19.65 | 0 | No findings | Irrelevant | Irrelevant
96. | Elementary School with a Kindergarten, Nižný Slavkov 72, 085 75 Nižný Slavkov | Modern education in the Elementary School with a Kindergarten in Nižný Slavkov 26110130441 | Nižný Slavkov 72, 085 75 Nižný Slavkov 29/10/2013 | 3382.15 | 2.52 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013 | The report was under the approval procedure as of 31 December 2013
97. | Municipality of Litava, Litava 5, 962 44 Litava | Increasing the education level of Roma at Elementary School in Litava 26130130064 | Litava č.5, Litava č. 4, 962 44 Litava 29/10/2013 | 19477.23 | 22.11 | 0 | No findings | Irrelevant | Irrelevant
98. | Municipality of Prenčov, Prenčov 300, 969 73 Prenčov | Further education for members of MRCs in the Municipality of Prenčov 26130130083 | Elementary School with a Kindergarten, Prenčov 203, 969 73 Prenčov, ZŠ s MŠ, Sv. Anton č.47, 969 72 Svätý Anton 30/10/2013 | 33 142,83 | 31.37 | 0 | No findings | Irrelevant | Irrelevant
99. | Elementary School, Ing. O. Kožucha 11, Spišská Nová Ves, Ing. O. Kožucha 11, Spišská Nová Ves | Education without barriers 26110130476 | Ing. O. Kožucha 11, Spišská Nová Ves 30/10/2013 | 76182.52 | 24.93 | 0 | No findings | Irrelevant | Irrelevant
100. | University of Economics in Bratislava, Dolnozemská cesta 1, 852 35 Bratislava | Increasing the quality of postgradual studies and promoting international research at the Faculty of National Economy of the Universtiy of Economics in Bratislava 26140230005 | Dolnozemská cesta 1, 852 35 Bratislava 05/11/2013 | 14231.75 | 2.53 | 0 | No findings | Irrelevant | Irrelevant
101. | Academy of Armed Forces of Gen. Milan Rastislav Štefánik, Demänová 393, 031 01 Liptovský Mikuláš | Improving the administration and managemnet of the AAF in LM 26110230008 | Demänová 393, 031 01 Liptovský Mikuláš 06/11/2013 | 152734.32 | 16.04 | 0 | No findings | Irrelevant | Irrelevant
102. | Slovak University of Technology in Bratislava, Vazovova 5, 812 43 Bratislava - Staré Mesto | Implementing an internal system of quality assurance in education 26110230042 | Paulínska 16, 917 24 Trnava 14/11/2013 | 54447.57 | 8.92 | 0 | No findings | Irrelevant | Irrelevant
103. | University of ss. Cyril and Methodius, Nam. J. Herdu 2, 917 01 Trnava | Improving the quality of education at the Faculty of Natural Sciences of UCM in Trnava in the study programme "Applied chemistry and biochemistry" 26110230051 | Nam. J. Herdu 2, 917 01 Trnava 14/11/2013 | 8203.98 | 2.5 | 0 | No findings | Irrelevant | Irrelevant
104. | Slovak University of Agriculture in Nitra, Trieda Andreja Hlinku 2, 949 76 Nitra | Creating a system of approval, monitoring and regular evaluation of study programmes 26110230049 | Trieda Andreja Hlinku 2, 949 76 Nitra 27/11/2013 | 13180.39 | 4.05 | 0 | No findings | Irrelevant | Irrelevant
105. | Elementary School – Alapiskola Rimavská Seč, Záhradná 31, 980 42 Rimavská Seč | Better life through reading literacy 26130130077 | Záhradná 31, 980 42 Rimavská Seč 03/12/2013 | 35730.51 | 15.17 | 0 | No findings | Irrelevant | Irrelevant
106. | University of ss. Cyril and Methodius, Nam. J. Herdu 2, 917 01 Trnava | Implementation of innovative models of quality assessment, monitoring and assurance at the Faculty of Massmedia Communication of UCM Trnava 26110230062 | Námestie J. Herdu 2 a Skladová 3, 917 01 Trnava 05/12/2013 | 43863.59 | 8.03 | 0 | No findings | Irrelevant | Irrelevant
107. | Slovak University of Technology in Bratislava, Vazovova 5, 812 43 Bratislava - Staré Mesto | Rationalisation and improvement of the study programme Industrial management to improve career guidance 26110230055 | Paulínska 16, 917 24 Trnava 05/12/2013 | 50050.21 | 22.36 | 0 | No findings | Irrelevant | Irrelevant
Source: IB MA

## MoH SR
List of on-the-spot inspections performed by the IB MA MoH SR from 01 January 2013 to 31 December 2013
Ref. No. | Name of Beneficiary | Project name/ ITMS code | Place and time of the physical performance of the on-the-spot inspection | Amount of funding checked | Amount of funding checked as percentage of eligible project expenditures | Amount of ineligible expenditures identified | Principal findings, incl. any discrepancies | Corrective measures proposed for detected shortcomings | Results of adopted measures
1. | Košice Self-Governing Region | Increasing the education level of medical staff in the Region of Košice II 26120230012 | Košice, Nemocnica Šaca a.s, 05-06/02/2013 | N/A | N/A | N/A | In order to settle the project´s financial relations, the Beneficiary is due to pay EUR 10,625.00 for EU funds and EUR 1,250.00 for state budget funds to the OFP account 7000289870/8180. The number of employees who completed the specialisation training needs to be proven by the Beneficiary by diplomas on specialisation in the respective field. | The Beneficiary is due to summarise the diplomas on specialisation in the respective fields of specialisation of the employees who completed the specialisation training within 14 days following the delivery of the On-the-Spot Inspection Report No. 1/2013 and send the diplomas to the IBMA. The Beneficiary is obliged to pay EUR 10,625.00 for EU funds and EUR 1,250.00 for state budget funds to the OPE account no. 7000289870/8180 within 14 days from the delivery of the On-the-Spot Inspection Report No. 1/2013. | The Beneficiary complied with the set measure on 25 March 2013.
2. | Trnava Self-Governing Region | Supporting the education of medical staff in the Trnava Self-Governing Region 26120230008 | Trnava, 28/02/2013 | N/A | N/A | N/A | The number of employees who completed the specialisation training needs to be proven by the Beneficiary by diplomas on specialisation in the respective field. | The Beneficiary is due to summarise the diplomas on specialisation in the respective fields of specialisation of the employees who completed the specialisation training within 14 days following the delivery of the Report on On-the-Spot Inspection No. 1/2013 and send the diplomas to the IBMA. | The Beneficiary complied with the set measure on 17 April 2013.
3. | Trenčín Self-Governing Region | Expanding the healthcare system with qualified medical staff in the Trenčín Self-Governing Region 26120230007 | Trenčín, 23/04/2013 | N/A | N/A | N/A | The number of employees who completed the specialisation training needs to be proven by the Beneficiary by diplomas on specialisation in the respective field. | The Beneficiary is due to summarise the diplomas on specialisation in the respective fields of specialisation of the employees who completed the specialisation training within 14 days following the delivery of the Report on On-the-Spot Inspection No. 1/2013 and send the diplomas to the IBMA. With respect to other medical staff who have not completed their specialisation training in the respective field of specialisation as of this date, the Beneficiary is due to send their diplomas of specialisation after receiving them from the medical facilities as an annex to the Follow-up Monitoring Report in line with the Manual for OPE NFC Beneficiaries. | The Beneficiary complied with the set measure on 15 May 2013.
4. | RZP - Asistenčné služby, s.r.o | Saving lives professionally and safely 26120230025 | RZP - Asistenčné služby s.r.o, Trenčín, 24/04/2013 | N/A | N/A | N/A | The control group found out that one instructor attended the training module in spite of the fact that the participation of two instructors is needed under Grant Contract No. 12/2011/OPV due to the interactive nature of work and exchange of professional experience. It was also found out that the training course did not take place at the set date and that the training extent was reduced by the Beneficiary. | Further to the findings of the on-the-spot inspection, the IBMA considers all expenditure related to the training activity of 24 April 2013 ineligible. The IBMA requested the beneficiary to present its opinion on the control group´s findings within 14 calendar days from the delivery of the report, and to take relevant measures to remedy and prevent the respective findings. | The Beneficiary complied with the set measure on 21 May 2013.
5. | Žilina Self-Governing Region | Supporting the education of medical staff in the Žilina Self-Governing Region 26120230011 | Žilina, 24/04/2013 | N/A | N/A | N/A | The number of employees who completed the specialisation training needs to be proven by the Beneficiary by diplomas on specialisation in the respective field. | The Beneficiary is due to summarise the diplomas on specialisation in the respective field within 14 days following the delivery of the Report on On-the-Spot Inspection No. 1/2013. | The Beneficiary complied with the set measure on 28 May 2013.
Source: IB MA